| 1. | a. Secretariat Social Service | To modernize the accommodation for efficient functioning of the Ministry and also provide information technology support. Maintenance of the office equipments and procurement of stationery. | 13.60 (a+b) | 3.00 (a+b) | Modernization of about 10 rooms in the ministry, Providing Web based delivery of the services and information of the ministry. Training of the employees of the Ministry in IT related areas and to upgrade LAN. | 42 computers with latest software along with printers were purchased. Training to the employees of the Ministry in IT related areas taken up as per requirement. | 10.28 | 1.87 | Also upgraded LAN. Modernization of rooms could not be taken up due to non-materialization of the project. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | b. Central Secretariat Library (CSL) | To provide information and research services to Academicians, Research Scholars and Policy Planners. It is the main reference library for all purposes. |  |  | To strengthen the reference and referral services of CSL. Conservation of 6000 thousand rare books. Renovation of main Reading Hall. Installation of RFID system in CSL. Acquisition of Micro Film rolls of Indian official documents. | Installation Wiring etc. for LAN work completed, extension of computer room and redesigning is under progress and will be completed by 31.03.2008, RFID Security System is under pipeline. A number of books have been added in English and in other regional languages, order placed to British Library London for acquisition of Microfilm rolls of Indian Official documents published during the British period. |  |  | Binding work is being done as a regular activity of the Library. |
| 2. | Zonal Cultural Centre | Aims at the promotion of Grassroot Culture and Cultural Kinships which transcend territorial boundaries and to arouse and deepen awareness of local culture. | -- | 13.00 |  |  | -- | 16.74 | Includes 30% provision towards pro-women, and 20% provision for ST allocation. |
| (i) | National Culture Exchange Programme | Exchange of artists, Musicians, performers, & sculptors etc. between different regions within the country for the promotion of rich cultural heritage of India. |  |  | About 1100 programmes would be organized benefiting a large number of artists. | About 675 programmes organized benefiting a large number of artists deployed at fairs, festivals, cultural events to disseminate the cultural diversity across the country. |  |  |  |
| (ii) | Documentation | Documentation of various folk & tribal art forms particularly the vanishing art forms for their proper preservation. |  |  | Various folk & tribal art forms, great masters of member states will be documented as per advice of Programme Committee and research oriented projects would be taken in hand for publication. | More than 63 documentation works have been taken up. |  |  |  |
| (iii) | Lok Tarang Folk Dance Festival 2008 | This festival is organized for Republic Day Celebrations during January each year for the promotion of our rich cultural heritage & national integration |  |  | This festival provides a unique performance opportunity for the folk artists from various parts of country at the national level. Besides this a large number of school children participate in R.D. Parade. | 7 ZCCs organized Lok Tarang from 24th Jan. to 29th Jan. 08 successfully. |  |  |  |
| (iv) | Kurukshetra Utsav | Celebrated on the occasion of Geeta Jayanti Samaroh at Kurukshetra-a Sacred place related to Mahabharta |  |  | Very suitable occasion for the promotion of Indian art & culture. Classical & folk artists perform benefiting large number of people. Besides this a large number of craft persons are given opportunity to display & sell their products | NZCC in collaboration with Kurukshetra Development Board organized Kurukshetra utsav and Geeta Jayanti Samaroh from 8th to 23.12.07. Renowned artistes and more than 2 lakh visitors participated. |  |  |  |
| (v) | Guru Shishya Parampara | For the promotion & preservation of our Fast vanishing art Forms |  |  | Not only Gurus but shishyas are also benefited. About 100 gurus with 500 shishyas are likely to be benefited during the year. | 147 gurus from various art from alongwith their shishyas benefitted. |  |  | Art forms are decided in Consultation with State Governments from time to time. |
| (vi) | Theatre Rejuvenation | Providing an opportunity to the theatre artists to stage plays & other theatre activities. Also interacting with each other on the Common platform |  |  | About 100 theatre groups would stage their plays and more than 1000 artists and a large number of people would be benefited in promoting the theatre. Workshops to promote theatrical skills will also be held. | This year, ZCC's have conducted various porgrammes in mode of theatre shows, theatre festivals, workshops and mythological theatre festival. Under this scheme 176 plays have also been staged. |  |  |  |
| (viii) | Young Talent Scheme | To recognize & encourage young Talented artists in various folk Art forms |  |  | About 100 folk art forms would be selected & competitions would be held involving sufficient number of upcoming artists & public. | More than 90 artistes have benefitted under this scheme. |  |  |  |
| (ix) | Shilpgram | Shilpgrams established by ZCCs are playing very significant role for the promotion & preservation of Indian Art & Culture and providing platform to the talented artisans. The main objective is to boost the activities in Shilpgram/ Kalagram |  |  | A large number of artists & artisans are benefited. A large number of people are made aware of our rich cultural heritage. | WZCC, Udaipur; SCZCC, Nagpur; EZCC Kolkata; NZCC, Patiala; organized Shilpagram Festival and other cultural event in their respective Shilpagrams involving a large number of artisan and craft men during the period. |  |  |  |
| (x) | Festival of the North East - OCTAVE | The objective of the proposed festival of the North East is to help the people in general and artists from the North East in particular to have a closer interaction with the rest of the country. |  |  | Around 500 artistes from North East including folk artistes, musicians, film & literary personalities etc. will be performing in this Annual event. | The N.E. Festival was held from 17-23 Feb. 08 at Trivendraum. |  |  |  |
| 3. | Sangeet Natak Akademi, New Delhi | The Academy devotes to the furtherance of the performing arts of India, and seeks to achieve this by arranging performances by renowned veterans as well as by talented artists of the younger generations through training programmes, award of scholarships and documentations. | 5.90 | 10.50 |  |  | 6.19 | 14.44 |  |
| (i) | Survey, Research, Documentation & Dissemination and Publication | Preservation and collection of recordings of rare traditions of Performing Arts, development of theoretical and academic knowledge of performing arts and publishing literature on performing arts. |  |  | 200 hrs of audio and video recordings, survey of performing arts of 5 states, release of 20 audio CDs, 10 video CDs, and 500 photographs, 50 hrs of audio and video dubbing. Two regional seminars and one national conference, Engagement of 5 scholars for encyclopedia on performing arts. | 345 hrs video and 102 hrs of audio recordings, 8765 photographs, 6 audio CDs, documentation on Puppet traditions Andhra Pradesh, Warangal. Seminars at Varansasi and Delhi 2 books 2 journals, 4 news bulletin, 1 Annual Report |  |  |  |
| (ii) | National Museum of Performing Arts, Library and Archive | Development of Academe’s existing museum musical instruments, puppets, masks and other art objects into a national level museum of performing arts by acquiring a separate building / campus. To develop an exclusive archive of audio video and photographic records of performing arts of India including a parallel archive in South India by acquiring rare collections scattered in the country and expansion of Akademi’s existing specialized library. |  |  | Acquisition of 2 acres of land, engagement of 6 project staff, preparation of 3 catalogues of existing collection, acquisition of 100 objects, organization of 3 workshops on restoration. Digitization of 500 hrs of existing archival holdings – acquisition of specialized equipment and project trained staff. Digitalization of 1,000 books, computerizing access for Library information facilities. | 2 Training programmes in Musical Instruments making started. Video digitalizing equipment acquired and installed and works started Acquisition of 303 books. Sangeet Natak Akademi has approached the Lt. Governor of Delhi for allocation of 5 acres of land for the proposed museum in Delhi.DDA is in correspondence with the Akademi in this regard. It is expected that suitable land will be made available in 2008. |  |  | The Plans for acquisition of land taken up with DDA. The construction of the proposed museum would be taken up soon after and would be completed within 2-3 year. |
| (iii) | National Institutes and Centres of Akademi for Specialized fields/ forms of India : Kathak Kendra, New Delhi, Kutiyattam Centre, Kerala, Chhau Centre, Baripada / Jamshedpur, Other National Projects, Jawaharlal Nehru Manipur Dance Academy, Imphal and Sattriya Centre, Guwahati | To create Kathak dancers of professional standing through well specialized training course, To upgrade and develop Akademi’s project support to Kutiyattam, Upgradation and development of the ongoing project support to Chhau Dances of Eastern region, Development of training programmes in traditional land folk theatre forms of India - Yakshagana of Karnataka, Bhagwat Mela of Tamilnadu, To create Manipuri dancers of professional standing through well specialized training course, Development of Akademi project support to Sattriya Dance and allied music and theatre traditions. |  |  | 3-4 new production of dance drama in a year, platforms to about 200 artistes and creating new audience for Kathak in the country. The ongoing project of Kutiyattam involving a number of projects training, production, research and performance directly benefiting about 400 artistes and scholars in urban and semi-urban areas. The ongoing project of Support to Chhau Dances involving a number of projects training, production, research and performance directly benefiting about 300 artistes and scholars in urban and semi-urban areas. 3-4 new productions of dance dramas in a year, platforms to about 200 artistes and creating new audience for Manipuri dance in the country The ongoing project on Sattriya Dance involving a number of projects training, production, research and performance directly benefiting about 300 artistes and scholars in urban and semi-urban areas. | Peripheral training centres starts in North, South and East Delhi; Kathak festivals held at Patiala and Jaipur; Kathak repertory created two new productions and performed in incredible India 60 at New York Kutiyattam Kendra Inaugurated in Thiruvananthapuram; Kutiyattam festival held, training programmes and activities started at 7 institutions, performances sponsored at different places. Ongoing project, training activities continued at Baripada, Rairangpur, Seraikella and Delhi; benefiting a large number of artists. Proposal for setting up of Chhanu Centre in Jamshedpur taken up with Government of Jharkhand. A large number of performances Chhau dances sponsored at different places in country. |  |  | Initiatives started for development of Akademi's specialized centres or projects in the areas of Odissi dance, traditional theatre etc. Target being achieved in Poorvang Nritya Parva, Dibrugarh Nritya Parva- festival of Sattriya Dance, Guwahati Regular activities of this national level institution were held including two new productions, outreach performances in North Eastern region and other states and holding workshop/lec-dam in other styles of dance. It is ongoing continued programme. 2 festivals of Sattriya dance organized. Support to 6 Sattras given. |
| (iv) | Training and Perform Support: Training and Preservation of traditional Folk & Tribal Performing Arts Sponsorship and promotion of young artists Assistance to Young Theatre Workers Promotion and preservation of puppetry Assistance and support to Contemporary and Experimental Works on Music, Dance, and Theatre Support to Children's Theatre (New Scheme) Certificate courses in identified areas of performing arts (New Scheme) | To support different forms of music, dance and theatre, encourage young members of the traditional arts, support to such forms, style, traditions, gharanas etc. that are threatened by change. To identify and promote talented young artistes of the country in dance and music and to subsidies and create new audiences. To support experimental works by young theatre directors, production of new plays, training for young theatre workers, upgrading standards in different regions. To provide to assistance and development of traditional and contemporary puppet theatre, preserve the richest heritage of puppetry in the world To support a contemporary expression and idiom of Indian dance and new compositions of experimental music and production of experimental theatre. To create cultural space for children’s theatre which appears to be shrinking. The aim is to intervene through launching a scheme for supporting activities in the domain of children theatre. Certificate Course : Objective: To provide quality training in identified areas such as lighting, stage craft, choreography and choral singing, conservation and management of performing art heritage. |  |  | Training programme including 100 artistes Four festivals of young musicians and four festivals of young dancers in North, South, East and West Zones, two festivals for North Zone. Workshop for Young Theatre artistes for different zones Monthly performances of puppetry and interaction programme in Delhi, financial assistance to almost 30 institutions, national and international exhibition of puppets and associated musical instruments, four training programmes in Rajasthani Kathputali making and manipulating. The workshop and festival of contemporary choreographers / composers / experimental works in theatre, financial assistance and individuals.. 2-3 workshops for children will be held in different parts of the country for the participants of the age group of 8-15 years. | 12 training programmes under Guru-Shishya Paampara continued in rare traditions, benefiting over 100 artists. 6 Nritya Pratibha and Sangeet Pratibha festivals for young artists held in Dehradun, Pune, Mangalore, Vshakhapatnam, Siliguri and Patna. Rang Pratibha Festivals held in J&K, Karnataka and Orissa; theatre workshop held in Chhatisgarh. Theatre festival for young directios of East Zone held in Patna. National Festival of Puppetry and exhibition held in Chandigarh; training programmes in Kathputli of Rajathan and Ravan Chhaya of Orissa continued; financial support o 25 puppetry instructions given. Festival of contemporary choreography held in Ahmedabad, Gujarat; subsidy given to 4 Gurus New Scheme not started due to lack of funds. |  |  |  |
| (v) | Festivals, Workshops and National Exhibitions 1. SNA Festivals, Workshops & Exhibitions 2. Collaborative Programmes with State Akademis, Organizations, Central Govt. Organizations & Major Cultural Institutions and Sponsored Programme (New Scheme) 3. Regular Programme in Meghdoot Theatre Complex | To preserve, promote and development of performing arts traditions in live practice on regional and national levels and support exchange of ideas, concepts and techniques nationwide. |  |  | - Lok Utsav – National Festival of Folk and Traditional arts - Theatre Festival and Seminar - National Festival of Andhra Dance Tradition and Seminar - Rang Sangam Festival of Theatre - Nritya Sangam Festival of Dance - Sangeet Sangam Festival of Music - Festival & Seminar on Theatre Music - Regional level celebration of Music Day, Dance Day & Theatre Day. - Two regional seminars on folklore. | OCATVE-2008, Trivandrum, Nritya Sangam, Jamshedpur; Sangeet Sangam, Indore; Rang Sangam, Mumbai; Festival & Seminar on Performing Arts of Mizoram, Music festical, Jammu, Rajiv Gandhi Birth Anniversary, Eastern India Folk Cultural Festival, Guwahati. 20 programmes were organized in collaboration with leading cultural institutions and State. Akademies/State Department of Culture. |  |  | Regular programmes in Meghdoot Theatre organized on puppetry and traditional theatre. |
| (vi) | Awards, Honours and Prizes : SNA Fellowships and Awards (Akademi Ratna Sadasyata and Puraskar) Yuva Puraskar (New Scheme) | To recognize excellence and sustained contribution in performing arts and support eminent old artists. A new scheme i.e. Yuva Puraskar in the name of Ustad Bismillah Khan has been constituted for the young artists of less than 35 years old. |  |  | 33 Awards and 5 Fellowships Mediclaim insurance for 350 Awardees and Fellows. 33 Awards to young artists. | 33 awards and 1 fellowship given by the President of India. To be held in March, 2008 |  |  |  |
| 4. | Lalit Kala Akademi | Promotion of visual and plastic arts | 4.10 | 5.50 |  |  | 3.65 | 5.71 |  |
| (i) | Promotional activities in the field of visual & plastic art. Art Development | The main objectives of the Academy are to provide infrastructural facilities to the artist’s community for the development of art activities of the country especially in the field of contemporary art. |  |  | Exhibitions: (Resonance, National, Outgoing, Incoming & Regional Art)10 (R) Delegates: visiting India from abroad-7(R) Delegates: visits to abroad – 5(R) Camps & workshops at National - 4 Regional - 6 (R) | # Propagation and popularization of interstate music, dance and drama Exhibition-9 Delegate-5 Visiting abroad-Nil Camps & workshops at National - 1 Regional - 3 |  |  | The Akademi proposed to built two Regional Centre one each in Kolkata and Shillong. Negotiation with the respective State Govt. is at final stage. |
|  | Com. Dissmn Outgoing Exh,. National Exh. Triennale Archives Lectures & Film Camps Library Cons & Restn. Grants to State Akademis. Regional Centres Scholarships |  |  |  | Scholarships - 40 Fellowship - 1 Memorial Lectures/ Workshops-1 (R) Art Publications Portfolios - 2 Journals(Hindi/ English)– 2/1(R) Artist Directory - 1 Regional Journals-2 (R) Reproductions - 5 Art Books - 3 Art Festival in North East – 1 North East Festivals in other cities - 1 | Scholarships - 27 Fellowship -1, Memorial Lectures/ Workshops - 1 Art Publications Portfolios - 1 Journals (Hindi)- 1 Regional Journals 1 Reproductions- 1 Art Festival in North East- 1 |  |  |  |
| 5. | Sahitya Akademi | To undertake publishing & promoting Indian literature | 4.00 | 9.75 |  |  | 4.20 | 10.55 |  |
| (i) | Upgradation of Libraries and Information Services | To provide readers/ intellectuals the complete range of books and update basic information about writers and literary activities in India at one place, make documentary tele films on eminent writers and scholars in the field of literature with modern archive unit of visuals. |  |  | Purchase of books in 24 languages. Subscription and New journals to be added. Upgradation of the Akademi’s web site and Hindi web site will be launched. Ten Documentary films on writers will be made. | Purchase of books in 24 languages, continued subscription to various literary journals/new journals made. retro-conversion of bibliographic data in Kannad, Malayalam, Bengali and Oriya also taken up upgradation of akademi’s web site and Hindi web site also taken up. |  |  | Development of archive unit continued by adding modern equipment 10 documentary films on writers made. |
| (ii) | ### Publication Schemes | The scheme to full fill the basic objective of the Akademi dissemination of Indian Literature and making available to multilingual societies of Indian Literary masterpieces from other language into their own language, histories of literature, monographs on Indian Writers, translation of important Indian and foreign classics, anthologies of poetry, short-stories, one-act plays, literary essays etc. |  |  | It is proposed to publish around 300 books in all the 24 languages recognised by the Akademi. The publication of bi-monthly journals Samkaleen Bharatiya Sahitya (Hindi) and Indian Literature (English) and a half yearly journal Sanskrit Pratibha (Sanskrit) to continue. | 295 books were published in 24 languages, bi monthly journal Samkaleen Bharatiya Sahitya (Hindi) and Indian Literature (English) and half yearly journal Sanskrit Pratibha (Sanskrit) publications continued |  |  |  |
| (iii) | Modernization and improvement of administrative functioning | To keep pace with the improved technology of the modern electronic age. |  |  | The computerization in the Akademi will be upgraded. The accommodation at New Delhi, Mumbai, Kolkata, Chennai and Bangalore on hire will continue. The interior of the Regional Office Kolkata office premises being purchased from Municipal Corporation Kolkata will be done. | The computerization in the Akademi upgraded by phasing out old computers with latest one, the fabrication/interior of regional office premises bought from Municipal Corporation Kolkata has been started by engaging architecture. |  |  | Training programmes, workshops etc. organized |
| (iv) | Literary functions and programme | To celebrate centenaries of great writers, hold regional, national and international seminars, writers camps, workshops, symposiums etc., provide writers a forum for their periodical gathering by organizing meet the author, men and books, Kavi Sandhi, Asmita for women writers, Katha Sandhi, Kavya Bharati, Mulakat, Samvad, Kavya Sandhya and Antral etc. |  |  | Around 35 Seminars including international seminars, Literary Forums, Men and Books, Katha Sandhi, Kavi Sandhi, Avishkar, Meet the Author, Through My Window, Asmita, Mulakat, Samvad, Book Release Functions and Sur Sahitya etc. | Held literary forum meetings, Men and Book, Asmita, Katha Sandhi, Kavi Sandhi, Avishkar, Meet the Author, Through My Window etc. also celebrated centenaries of important writers. 80 Seminars at Regional, National and International levels and 150 Literary Forum Meetings were organized. |  |  |  |
| (v) | Awards to writers | To enable young and old writers in Indian language to visit other parts than their own, send Indian writers and host foreign writer delegation under Cultural Exchange Programmes, to give award to literary works which merit appreciation and encouragement in all 24 Indian languages recognized by the Akademi, give honorary fellowships to eminent writers in recognition of their contribution to Indian Literature. |  |  | Around 50 young writers to avail the Travel Grant scheme of the Akademi. The Akademi will participate in different Cultural Exchange Programmes including new ones as per the decision of the Government of India or on reciprocal basis. The Annual Awards will be given to writers in 24 Indian languages recognized by the Akademi. To conduct meetings of the 24 language advisory boards besides other committees. | Around 50 young writers availed the facilities under Travel Grant Scheme. Participated in different Cultural Exchange Programmes as per decisions of the GOI. Annual awards given to writers in 24 Indian languages recognized by Akademi. Assistance to other literary organizations at State level continued. |  |  |  |
| (vi) | Promotion of akademi publication, advertisement publicity and book exhibitions | To advertise Akademi publications through literary journals, organize and participate in book exhibitions at regional, national and international level. |  |  | The Akademi will participate in around 90 book exhibitions at National/ Regional / International (Lahore / Frankfurt) levels. The Akademi proposes the sales target around Rs.250 lakhs for the year 2007-08 The target is to be achieved by participating in various book exhibitions at national/ regional levels. | Akademi achieved a sale target of Rs. 230.00 lakh, the Akademi is participated in 95 book exhibitions at Regional / National levels. Publication of the akademi were published through advertisement, reviews etc. in newspapers/ important magazines. |  |  | A book shop was also inaugurated at Puducherry. |
| (vii) | ##### Translation schemes | Translation is the basic activity of the Akademi. The translation centre “SABDANA” will be strengthen to make arrangements for training of translators and train the practicing translators by conducting workshops, to do the inter-lingual research and translation, prepare a register of translators and identify titles for translations and their publications into other Indian languages and into foreign languages. It is proposed to establish a few more Translation Centers on the lines of SABDANA. |  |  | The Translation Prizes in 24 languages recognized by the Akademi will continue. The Translation Centers at Bangalore and Kolkata are likely to publish more than ten books in regional languages and English. Besides publication by the Translation Center will continue by translating important books in various Indian languages and vise-versa. The Centers will conduct Translation Workshops in languages recognized by the Akademi as well as un-recognized languages to strengthen the translation activities. New Translation Centers will be launched in Western and Northern regions. | Translation Prizes in 24 languages were given at the function held at Hyderabad. Translation centers at Bangalore and Kolkata have undertaken the work to published more than 10 books in regional languages and English. Translations Centres continued its activities by translating important books in various Indian languages & vise versa. It also continued its activities of conducting translation workshops and also translation of children literature into recognized languages. |  |  | Work on 20 classics in fictions and 50 other books continued. |
| (viii) | Regional literary Study project | To strengthen the inter-regional studies as also comparative studies with one linguistic group of language and literatures to another by the Regional Boards. The scheme envisages conducting workshops, seminars and writers meet at regional and national level. |  |  | Meetings of all the four Regional Boards will be held as per schedule. The work on printing of works shall be taken up. Recommended seminars / workshops will be held | Meetings of all the four Regional Boards held as per schedule. The recommended seminars/workshops being organized. |  |  |  |
| 6. | Festival of India | To organize major cultural festivals in selected foreign countries for achieving better understanding and cooperation | 4.00 | -- | To hold “India Week” in Brazil. Organization of “ Festival of India” in United Kingdom is under process. | Participation of Indian Cultural Troupe in the 40th Session of international Festival of "Sahara of Douz" held from 26-29 December, 2007 in Tunisia . India @ 60 event was held in New York during Sep. 23-26, 07 | 3.30 | -- |  |
| 7. | Indira Gandhi National Centre for the Arts (IGNCA) | IGNCA was established to commemorate the memory of the Former Prime Minister Late Smt. Indira Gandhi. It and envisioned as a centre for research, academic pursuit and dissemination in the field of the arts. | -- | 45.00 |  |  | -- | 40.15 |  |
| (i) | Construction of Buildings | Completion of two buildings and construction of concert hall. |  |  | (i) Completion of Kalanidhi-Kalakosha Building in all respect. (ii) Foundation work in Sutradhara Building. (iii) Preparation of estimates, architectural drawings | Full operationalisation of the Kalanidhi-Kalakosha Building including guest house block. |  |  | (1) out of approved Plan Budget of Rs. 21.65 crore has been sanctioned. |
| (ii) | Promotion of Multidisciplinary Research and Critical Dialogue among diverse Arts. | Enlarge its programme of research and publication of fundamental texts, reference works, glossaries, dictionaries, encyclopedia, comparative history of Indian arts, thesaurus of fundamental terms, inter-dialect and inter-disciplinary glossaries and dictionaries, explore relationship of arts and science, dimensions and explore relationship between arts of India and the world, special focus on the North-East and its cultural dimensions. |  |  | Studies on the following dimensions: (a) Multiple levels of identity and their manifestation in Arts. (b) Language and Cultural Diversity (c) Wisdom Tradition, Ecology, Resource Management and Sustainable Development. (d) Religious Identities, Confluence of Traditions and composite Cultures. (e) Inter-Cultural Dialogue. (f) Contribution of Women to Indian Art and Culture. | (a) Publication of critical editions of fundamental texts, monographs on tribal and folk culture, republication of texts by eminent scholars (b) Research and field studies. (c) Audio-video documentation (d) Conference, seminars and workshops (e) Exhibition and multi-media events (f) Production of films, CDs, audio-video recordings. |  |  | Out of approved Plan Budget of Rs. 28.35 crore for the schemes, an amount of Rs. 12.00 crore only was released on 31st Aug, 07. Most of the schemes/ Projects have been completed. The rests are at on going stage. |
| (iii) | Resource augmentation and modernization | Augment the repository of primary source material – written, oral, auditory, audio-visual and pictorial of the IGNCA, to serve as the national centre for the arts and culture and support research and publication activities of its other in-house divisions, Upgrade and install modern management and technological tools and systems, Upgrade technology and set-up permanent galleries for display and exhibition. |  |  | (a) Purchase of Books, Journals, Rare Books & Personal collections. (b) Collection of slides through in-house digital photography and Purchase of slides (c) Microfilming of Manuscripts (d) Acquisition of Cultural archival material (e) Modernization of Digital Library, Annonated Bibliography Index, Reprographic unit & Audio-visual equipments (f) Cultural Informatics (g) Creation of Galleries | (i) Addition of books, periodicals, journals in the Library (ii) Modernization of the Library services State-of-art equipments in Reprography7, Computer centre and media production (iii) Setting up of three galleries for display of arts and crafts (iv) Digitization of manuscripts, internal repository etc. (v) Operationalising e-governance in the cultural field. (vi) Collection of archival material from the North-East |  |  | Out of approved Plan Budget of Rs. 28.35 crore for the schemes, an amount of Rs. 12.00 crore only was released on 31st Aug, 07. Most of the schemes/ Projects have been completed. The rests are at on going stage. |
| (iv) | Cultural Cartography | Map ecological and cultural profile of diverse communities of India along with specific aspects of art and crafts traditions prevalent among them. |  |  | (i) Creation of a Cell (ii) Research and field study (iii) Preparation of Atlas. | (i) Training and capacity building (ii) Publication (iii) Seminars, conferences and workshops. | . |  | Due to cut in the budget allocation for 2007-08, these projects will be taken in the next year. |
| 8. | National School of Drama, New Delhi | Promote Theatre and to conduct theatre training programme | 4.45 | 11.00 |  |  | 4.60 | 16.50 |  |
| (i) | Theatre workshop and part time courses in regions and locally and other training courses for faculty and staff. | To benefit a vast majority of theatre enthusiasts in various states with diverse languages and cultural backgrounds and to create theatre awareness in them. |  |  | 10 theatre workshops to be conducted. 15 Theater Groups to be Assisted. 2 Part time Courses will be conducted. 3 Teachers training and refresher course for faculty & staff. 10 Collaborative workshops with theater groups. | 52 theatre workshops and 2 part time courses were conducted. About 140 theatre experts and 30 daily wagers workers are being benefited. Theatre training has been provided to 850 children. |  |  |  |
| (ii) | Organizing of course of training Children Theatre in Delhi and outside Delhi | To develop personality and give exposure to children in terms of their expressions and confidence. |  |  | 15 children theatre workshops, 10 Collaborative theater Workshops &12 theater groups will be organized/given FA. | 15 workshops, 3 Collaborative Theatre workshops were conducted Theatre training has been provided to 450 children |  |  |  |
| (iii) | Organizing of collaborative programme of traditional group in villages and theatre festival/ exhibition. | Providing 3-year Advanced Dramatic Training Course and to acquaint the students from theatre from existing in different regions of the country. |  |  | 6 collaborative programmes. 2 Festivals are to be conducted. 20 exhibitions of plays are to be displayed. 35 contractual experts will be benefited. | Conducted summer festival of 16 days comprising weekend theatre performances- 8, displayed exhibitions-3, fellows and students-2 and visit to foreign countries-1 |  |  |  |
| (iv) | Promotion of Folk, Tribal Arts and Educational Tours | To familiarize the students with the existing folk and tribal art relating to theatrical and music forms. |  |  | 3 Performances of Folk and Tribal to be held in Orissa, Educational tours for the students will be conducted and also performances with tribal groups to be organized. | Conducted one long production oriented workshop in Jamshedpur in June-July 2007 with the students of second year. |  |  |  |
| (v) | Formation of Repertory Company of Adults performing for children | Aim to promote theatrical performances for children. |  |  | Summer festival in 12 centres in Delhi and outside Delhi. 15 Saturday and Sunday club performances. 12 performances with invited groups. 5 workshops with children teachers. | Production of new play, summer theatre, Sunday Club teachers festival other festival workshop and place in school were conducted. Performances of plays before public and schools organized. |  |  |  |
| (vi) | National Theatre Festival & Satellite Theatre Festival | To conduct National Festival. |  |  | 10th BRM and Satellite Theater festivals are to be conducted with Indian and foreign theatre groups to be held in January, 2008 | Festivals are scheduled to be organized in January, 2008 including satellite theatre festival in Mumbai |  |  |  |
| ### 9. | ### National Gallery of Modern Art (NGMA) | ### To create an understanding and sensitivity among the Indian public towards visual and plastic arts in general and to promote the development of contemporary art in particular. | ### 1.75 | ### 4.50 |  |  | ### 1.62 | ### 2.34 |  |
| (i) | ### Upgradation, Modernization and maintenance of museum | ### To promote development of contemporary art at par with international level. |  |  | Maintenance of a well displayed Gallery at par with International standards both at New Delhi and Mumbai. Operationalisation of a new branch of NGMA at Bangalore and a new wing of the Gallery at New Delhi. Organisation of at least 8 special and retrospective exhibitions of renowned Indian artists and 2 exhibitions of contemporary foreign artists under cultural exchange programme. Development of Sculpture Garden at NGMA, New Delhi. To organize summer art workshop during May-June, 2007. To organize 300 film shows and also 6 5 conducted tours to be organized for the benefit of the school children. Around 35 thousand persons expected to visit the museum and benefit from its presentations and other activities. | ### In addition to maintaining a well displayed gallery NGMA organized: ### 11 special exhibitions both at Delhi and Mumbai, 277 films shows, 158 conducted tours, Art Sketch Club held every Sunday, Summer Art workshop, 2 seminars on art and art practices, 7 catalogues and 9 posters of special exhibitions, 5 different colour reproductions and 8 Greeting card of various art works, produced 21 conducted tours of the galleries for sponsored groups and VIPs arranged, restoration of 120 art objects and cleaning and conditioning of 460 art objects undertaken. About 40,000 persons visited the galleries. |  |  |  |
| 10. | Asiatic Society Kolkata | Declared as an institution of national importance. To launch research projects on language, literature, culture and socio-economical aspects | 5.00 | 3.00 |  |  | 4.76 | 3.25 |  |
| (i) | Development of Library System | To establish build, maintain institutions for promotion of research in humanities and sciences |  |  | (i) Book acquisition- 2,000 (ii) Micro film acquisition exposure- 20,000 sheets (iii) Cataloguing : Rare Books- 5,000 Nos. (iv) CD ROM Acquisition – 3,000 sheets (v) Binding/ Mending - 4,000 nos. | Book acquisition-3196 vol. Subscription to serials-20 titles Rare books-2335 General books & Journals-2335 Books & Journals-2162 |  |  | Continuous Process |
| (ii) | Development of Museum & User facility | To preserve manuscripts which has a rich collection of archival records, coins inscriptions and very valuable lithographs. |  |  | Cataloguing/Documentation of MSS, archival Material etc. – 5000 MS, 1000 letters, 200 others | MSS-1981 Archival files-71 Letters-4271 |  |  |  |
| (iii) | Conservation & Preservation of rare books, MSS & Other document | To take effective measure for the preservation of brittle and fragile manuscripts, rare books and other ancient objects kept in the Museum and Library of Society. |  |  | Restoration of 3000 sheets of Lithographic prints. | Rare books, mss, paintings etc. of library, museum, and from other departments preserved by taking effective measure |  |  |  |
| (iv) | Augmentation of Research | Research work in different areas, imparting training, conduction seminars, lectures, workshops etc. |  |  | 35 projects, 12 Seminars, 25 Lectures, 3 Training Programme, Exhibitions/ Workshops. | 27 research projects,11 seminars, 2 lectures, 1 training programme/ workshop held |  |  | Continuous Process |
| 11. | Centre for Cultural Resources and Training, New Delhi | Aims to improve the quality of life through the medium of Academies working in the field of linking education with culture. | 2.30 | 8.50 |  |  | 2.16 | 11.35 |  |
| (i) (ii) | Propagation of Culture among school students Cultural Talent Search Scholarship Scheme (CTSS) | To conduct a variety of in-service Teacher Training Programmes such as Orientation Training Programmes, workshops, Seminars, Refresher course etc. in different parts of the country for school teachers, teacher educators etc. organisation of educational activities for school students and children belonging to governmental and non-governmental organizations. Workshops for children of resettlement and basti colonies and for physically challenged students. Aims at providing facilities by awarding scholarship to study the performing and other arts to outstanding young children in the age group of 10-14 years. |  |  | Orientation -5000 Teacher Educators/ In-service School Teachers Training Porgrammes/ Seminars/ Workshops/Refresher Course for Teacher Educators/in-service Teachers Teachers to be trained through Trainers-2000 Teachers Settingup of Cultural Clubs - 100 Students to be trained under Community and Extension Programmes-40000 Students # Production Video films including CD Roms- 4 Publications including reprints -15 Cultural Kits-800 Award of Scholarship under Cultural Talent Search Scholarships Scheme-400 2 Cultural Festival to be organized for scholarship holders. | 4800 Teachers/Teacher Educators have been trained in various Training Programmes. 3347 Teachers trained through Trainers. 25912 students have been trained. 91 Culture Clubs have been setup in various states in the country. Production 4 Video films including CD ROMs have been produced. 21 publications including reprints have been published. 874 sets of Cultural Kit have been distributed to the participating Teachers and Teacher Educators. 400 Scholarships have been awarded covering all parts of country including the North-East 2 Cultural Festival have been organized for scholarship holders |  |  |  |
| 12. | Financial Assistance for Professional Groups and Individuals for specified performing art projects. (Dance, Drama and Theatre Ensembles) | To promote the Guru Sishya Parampara and support organizations / individuals working in the field of Performing Arts. | 1.35 | 11.00 | About 1000 organizations/ individuals will be promoted and supported. | 445 individuals/ Professional Groups working in the field of performing arts promoted and supported. | 0.77 | 10.85 | Include 30% provision towards pro-women specified programme and 20% provision for STs population |
| 13. | Gandhi Peace Prize | Government of India announced institution of an annual international Gandhi Peace Prize for social, economic and political transformation through non-violence and other Gandhian methods as a part of celebration of 125th birth anniversary of Mahatma Gandhi. | 1.30 | -- | The recipient of this prize is selected by the Jury headed by Hon’ble Prime Minister in accordance with the prescribed code of procedure. | It is under process | -- | -- | Gandhi Peace Prize 2005 has been awarded to Archbishop Desmond Tutu. |
| 14. | National Culture Fund (NCF) | Public Private Partnership in the sphere of culture. To mobilize the funds from corporates/PSU & for funding of conservation and other cultural activities. | -- | 3.00 | Projects of NCF are for preservation of both tangible and intangible aspects of India’s rich cultural heritage. For this purposes many ongoing projects are being implemented. | Out of 8 projects 3 projects have already been completed and the work under 5 projects is under progress. The completed projects include the main Humayun's Tomb Complex, illumination of Jantar Mantar New Delhi, structure repair of Shaniwarwada, Pune | -- | 3.00 |  |
| 15. | Centenaries/ Anniversaries Celebration | To celebrate the Centenary/Anniversary of important personalities and events | 15.07 | 19.00 |  |  | 10.67 | 3.73 |  |
| 15.1 | Celebration of 2550th Anniversary of Mahaparinirvana of Lord Buddha | To highlight salient aspects of the life and times of Lord Buddha and to acquaint the people particularly the young generation with the great soul, who successfully diverted the attention of masses towards Ahimsa for the betterment of human. |  |  | Programmes are to be organized in memory of Lord Budha and funds will be provided for the projects associated with Lord Budha to strengthen the infrastructure to propagate the teachings of Lord Budha. | Apart from the programmes/projects being organized in the memory of Lord Buddha, 30 NGOs have also been assisted for propagating the teaching of Lord Buddha & related issues. | 2.47 | -- |  |
| 15.2 | Celebration of Birth Centenary of Lal Bahadur Shastri | In order to create a Chair in the Institute of Defence Studies and Analysis, N.Delhi in the name of Shri Lal Bahadur Shastri. |  |  | A provision of Rs. 7.00 lakh has been kept for this purpose. |  | -- | -- |  |
| 15.3 | Celebration of 150th anniversary of 1st war of independence, 1857. | To highlight the sacrifices of our great heroes / leaders who laid their life for freedom of the country and to pay home-age to them. To make aware the people specially young generation about the history of our freedom struggle to infuse into them the spirit of the National Integration and also highlight the achievement of Nation in various areas in past 60 years. |  |  | To celebrate the event, programmes will be organized in memory of great heroes/ leaders to educate the people. funds will be provided for maintenance/ restoration of monuments and places associated with the event. | In order to celebrate 150th anniversary of the 1st War of Independence, 1857 MoC released funds for inaugural function held in May 2007, main function organized by NCT of Delhi, organized Birth Centenary of Shaheed Bhagat Singh at Amritshar, organized event "Quit India Movement" at Mumbai, Mobile exhibition on Train organized by I&B and Railway Min. | 35.58 | -- |  |
| 15.4 | Financial support to Khalsa Heritage Project | To highlight salient aspects of the important events relating to Khalsa Heritage in order to infuse in the public, particularly the young, the spirit of these great events. |  |  | Funds for Khalsa Heritage Project to be given to Punjab Govt. as 1/3rd share of Central Govt. (Plan) as reimbursement of the amount spent on the project on quarterly basis. | Funds to the tune of Rs. 4.93 crore have been released to Punjab Govt. for KHP. | -- | 4.93 |  |
| 16. | Other Schemes |  | 37.37 | 88.84 |  |  |  |  |  |
| (a) | # Central Institute of Higher Tibetan Studies, Sarnath | Established with a view to educating the youth of Tibet and Himalayan border areas of India | 4.90 | 3.00 |  |  | 4.52 | 3.00 |  |
| (i) | Development of Library | ## 1.To Preserve Tibetan culture and tradition. ## 2.To restore ancient Indian sciences and literature preserved in the Tibetan languages. |  |  | Purchase of 200 books, equipment and other material for its maintenance and development. | About 210 books were purchased alongwith computers and equipment/ other material for maintenance and development of library. |  |  |  |
| (ii) | Publication and Printing. | To provide printed material on Tibetan culture for scholars and others |  |  | 8 books to be published. | 9 books were published and got printing. |  |  |  |
| (iii) | Rare Buddhist Text Research | To offer the alternative educational facilities to the students of Indian border area who formerly availed the opportunity of receiving higher education in Tibet |  |  | Workshop, Publication of Dhih journals and infrastructure to be held. | Under Research Unit, 2 sites were visited for collection rare Buddhist Text. |  |  |  |
| (b) | Central Institute of Buddhist Studies, Leh | To develop multifaceted personality of the students through inculcation of the wisdom of Buddhist through and literature as well as to familiarize them with modern subjects to acquaint them with collection, conservation, translation, publication of rare manuscripts and research works relevant to Budhist Studies etc. | 3.00 | 7.50 |  |  | 3.20 | 5.94 |  |
| (i) | Construction of Building | Construction of Physical Infrastructure for CIBS and DPS, Zanskar. |  |  | To adhere to the time schedule in the past. | The construction is going on through CPWD and State PWD |  |  |  |
| (ii) | Provision for existing Gonpa/ Nunnery school | To support educational activities in the number of Gonpas by providing teachers and stipend to the students. |  |  | 29 Gonpa/Nunnery schools are going on. Approval of opening 21 Gonpa/Nunnery schools has also been obtained from Govt. of India, Min. of Culture. | 26Gonpa/Nunnery schools are running successfully attracting students form far flung areas. |  |  |  |
| (iii) | Other Activities under Plan like Publication of rare Books, Manuscripts Seminars/ Symposium, conduct of Refresher courses, Purchase of Books, Fuel, Furniture/Furnishing items, Machine/ Equipments, etc. | These are the continuing activities of the academic nature and for efficient running of the Institute. |  |  | Continuing schemes will be dealt with by the organization as usual. | These are the ongoing activities of the institution and are being carried out during the year as scheduled by the institute. |  |  |  |
| (c) | Gandhi Smriti and Darshan Samiti | To propagate the life, mission and thoughts of Mahatma Gandhi by organizing various socio – educational and cultural programmes. | 3.00 | 6.00 |  |  | 2.79 | 6.80 |  |
| (i) | Promotional Activities | To plan and carry on activities for the promotion of Mahatma Gandhi’s ideals and of national causes identified by him. |  |  | Regular programmes with educational institutions, programmes for youth, programmes to mark the 100 years of Satyagrah: Gandhi and the contemporary world commemorative programmes. | As a part of promotional activities regular interaction with children; exposure visit to Gandhi Smriti; quiz; discussions and competition on variety of social and developmental issues, bringing out the children’s newspaper, The Yamuna were taken up. Extensive summer school programmes were organized in various state like Karnataka, Himachal, Chandigarh, Delhi etc. |  |  |  |
| (ii) | Dissemination | To undertake such activities as will lead to greater understanding of Mahatma Gandhi’s life, work and thoughts. |  |  | Publication of journals, books etc., research activities and strengthening of International Centre for Gandhian Studies and Research Training Seminars/ Workshops. | The publication has mentioned in column 5 were published as per their periodicity. |  |  |  |
| (iii) | Infrastructure and Development related activities | To acquire, maintain and preserve the personal papers and other historical materials pertaining to the life and works of Mahatma Gandhi in consultation and collaboration with the other Governmental organizations engaged in Gandhian work. To preserve and maintain Martyr Column at Gandhi Smriti and pavilion at Gandhi Darshan Complex. |  |  | Development of Gandhi Smriti and Gandhi Darshan Complexes; restoration of Gandhian Heritage and acquisition of art, objects, book etc. purchase of modern office equipments etc. strengthening of Samiti’s infrastructure. | The development works were taken up through out the period under review. |  |  |  |
| (iv) | North East | To spread ideas and thought of Mahatma Gandhi in North-East. |  |  | 8 special programmes will be organized in the North-East Region. | During the period under review, the Samiti organized a series of conventions, Gandhi Quiz, initiated development activities in Gandhi Mandap etc. |  |  |  |
|  | Nava Nalanda Mahavihara, Nalanda, Bihar | To revive past glories of the ancient university of Nalanda and to give post graduate studies and research in Pali language and literature and Buddhology. | 1.30 | 3.00 |  |  | 1.27 | 2.05 |  |
| (i) | Improvement & Development of Library Service | Developing the library with purchase of new books on Pali, Buddhism Philosophy, ancient History, Culture and Architect, Hindi, English, Sanskrit etc. |  |  | Around 1000 books are expected to be purchased | About 1000 books were purchased. |  |  |  |
| (ii) | Development of Xuan Zang Memorial Hall | To provide creative works, as paintings, murals inside and outside the XHM and on landscaping etc. |  |  | Procurement of various paintings and murals connected with the life of Xuan Zang. | Various paintings and murals connected with the life of Xuan Zang have been procured. Further tenders from specializes agency and expert of the creative works have also been contracted. |  |  |  |
| (iii) | Construction of 100 beded new hostel | To accommodate the foreign students |  |  | Fund will be released to CPWD | To be carried out through CPWD on call of tenders. |  |  |  |
| (iv) | Purchase of Computer accessories and other electronic equipments | To establish in institute a complete information Technology with computers & net working system and also purchase of modernized equipments. |  |  | Running & maintenance expenses on the computers already existing and purchase of a few more. | New computer were purchased. |  |  |  |
| (v) | Cultural Exchange programme, workshops seminars & conferences | Promotion and dissemination of Buddhist thoughts by organizing seminars, workshop etc. on inter-institution exchange basis. |  |  | A part from several workshops and National Seminars on Relation in Linguistic, Social and Philosophical Perspective was organized. | Around 8 workshops, and 2 seminars and a couple of cultural programmes were organized. |  |  |  |
| (vi) | (i) Annual foundation day & ceremony & special convocation (ii) Award of scholarship to the meritorious students of Mahavihara | To commemorate the foundation day of the NNM on the 20th Nov. each year and special convocation. To support the meritorious students |  |  | Erudite scholars from interstate area, high official dignitaries, cultural programmes to grace the occasion. Indian and foreign students are to be benefited. | Foundation day and special convocation held as usual. Indian and foreign students were benefited through this scholarship scheme. |  |  |  |
| (vii) | Printing of old and new publication and documentation exhibition | Main objective is to print and reprint of the proceedings of the earlier seminars and other research oriented materials and to promote & dissemination of Lord Buddha’s teachings by holding exhibition & its documentation |  |  | Printing of proceeding of National Seminars, Commemorative volume and Annual Report etc. A Bihar’s Indic Spiritual, cultural Festival was organized. | Publications of research volumes and monographs were undertaken during the year along with publication of manuscripts |  |  |  |
| (viii) | Pali Hindi Dictionary Project | Scheme aims at preparing an exclusive Pali-Hindi Dictionary |  |  | With approval of BOM 3 reputed scholars on fixed remuneration are employed. | Compilation work of a Dictionary is in progress. 1st volume Part-I has been released. |  |  |  |
| (e) | Maulana Abul Kalam Azad Institute of Asian Studies, Kolkata | To conduct research and training of life and works of Maulana Abul Kalam Azad with the study of social culture, political and economic movement in Asia from the middle of the 19th century. | 0.56 | 4.00 |  |  | 0.46 | 4.47 |  |
| (i) | Research project including North East/ fellowship and other promotional activities. | To carryout research activities and revelation of political, social & economic changes in India and other Asian countries. |  |  | 30/40 Fellows will be engaged to under take Research on various areas including North East India. In addition to this new campus will provide hostel facility to out station fellows. Foreign visits & seminars at National & International level will be conducted. | 30/40 Fellows were undertaken Research on various areas. 1) Fellows participated in seminars on North-East & other areas regularly. 2) 11 Books have published at regular intervals over the year. 3) Field Work was undertaken by different Fellows at regular intervals. 4) 3 Nos of International Seminar organized by the Institute in different areas during 2007-08 |  |  | As a problem linked to organization of field work and seminar. |
| (ii) | Construction of Office Building & Hostel | To accommodate office staff, work station of fellows, Seminar Halls & Hostel facility. |  |  | Construction of 3 storied building for better functioning of officers/staff & Fellows. | Construction of 3 storied Building for better functioning of the officers/staff & Fellows, Library & Hostel Facilities with a cost of Rs. 6.00 Crores. We have already been paid Rs. 2.53 Crores & it is expected that an amount of Rs. 0.90 Crores will be payable by end of March 08 Rs. 2.00 Crores will be paid to CPWD for providing furniture ,electrical connection ,Stock for Library etc |  |  | Availability of Fund & completion of work by the contractor engaged by the C.P.W.D. |
| (iii) | Publication |  |  |  |  | 15 publications of books and one Journal were planned. |  |  |  |
| (iv) | Maulana Azad Museum | To establish a museum in honour of Maulan Azad at his residence at 5, Ashraf Mistry Lane, Kolkata-19. Contribution of Maulana Azad to Indian Independence movement along with a collection of memorabilia are on display for the visitors |  |  | Few dozens of photographs with caption and about a hundred memorabilia with LCD T.V. and the highest National Award – Bharat Ratna will be displayed. | A few dozen photographs with caption and about a hundred were collected & maintained together with memorabilia with the highest National Award - Bharat –Ratna displayed. Memorabilia and photographs are open to the public. An LCD TV shows footage on Maulana Azad |  |  |  |
| (f) | Kalakshetra Foundation, Chennai | A Cultural institution of International repute established for preservation of traditional values in Indian Art especially in the field of dance and museum. | 2.90 | 2.50 |  |  | 2.90 | 2.06 |  |
| (i) | Capitals Works/Building Projects | To provide an upgraded audio and lighting equipment for the theatre, renovation of hostel block and refurbishing of Museum |  |  | Renovation of hostel kitchen and refurbishing of Rukmini Devi Museum | Thatched roof over Rukmini Arangam and construction of Montessori block and modernized kitchen an dinning hall was completed. |  |  |  |
| (ii) | Upgradation of the Theatre-Civil works. | The existing construction of theatre is in very bad shape and had not been upgraded so far. To improve the facilities in the dressing rooms, toilets and to be in line with the modern facilities. |  |  | The number of dressing rooms for male and female artists will be assessed based on the maximum number of the artists who may use the facilities at a time. | Construction of toilets in CERC, water sewage connection process with CMWSSB were completed. |  |  |  |
| (iii) | Revival and documentation of dance dramas. | To document the 23 dance dramas choreographed by Smt. Rukmani Devi Arundale. |  |  | Six numbers of dance dramas will be documented and recorded in DVDs. They are being done in phased manner. To start with the 6- part Ramayana will be completed. | These works were completed during the year. |  |  |  |
| (iv) | Research and Library Building | To make the modern library with full-fledged facilities for preservation and for taking copies etc. |  |  | The library has around 4000 volumes of old and rare collection of books on music and dance and more than 3000 volumes of books on different subjects. These books will be properly mended and laminated wherever the need arises and properly catalogued. | Purchase of books for library and costumes theatre upgradation were undertaken during the year. |  |  |  |
| (g) | Namgyal Research Institute of Tibetology, Sikkim | The Institute is an autonomous organization under the state govt. of Sikkim and gets regular grant- in- aid from this ministry. The main objective of this institute is to spread the knowledge of Chhos(Doctrine of Buddha). | 0.40 | -- | The Institute has ongoing programmes of translating and publishing the seminal texts preserved in its archives. | The institute continued its ongoing programmes during the period under review | 0.40 | -- |  |
| (h) | a) Fellowship to outstanding artists in the field of performing, literary and visual arts. | This scheme provides financial support to outstanding artists in the fields of music, dance, theatre, visual art, literature and traditional art forms of folk and indigenous art. | 1.10 | 4.50 | 85 junior and 85 senior fellowships to be awarded. | 1383 artists were benefited under the scheme in the period under report. | 0.79 | 4.50 |  |
|  | b) Scholarship to young workers | This scheme seeks to give financial assistance to young artists of outstanding promise for advanced training within India. | 0.70 | -- | 400 scholarships to be awarded. |  | 0.44 |  |  |
| (l) | International cultural activities & grants to Indo-Foreign Friendship societies | To foster closer friendship and cultural contacts between India and the foreign country concerned. | 0.05 | -- | Grants are sanctioned on the specific recommendations of the Indian Mission concerned. The grant covers expenses of grantees on cultural activities. | 4 societies have so far been given grants under the scheme. | 0.47 | -- |  |
| (m) | Financial Assistance to distinguished art persons | To provide financial assistance to artists whose contribution in the field of art has been of great significance and who have attained an age of 58 years and above and are in indigent circumstances. | 1.55 | 3.00 | 1540 old artists to be provided assistance under this pension scheme. | Financial assistance was given to1091artists during the period under report. | 0.04 | 2.53 |  |
| (n) | #### Delegation under Culture Exchange Programme | ## Promotion of Cultural relations with other countries of the world on the reciprocal basis. | 0.80 | -- | The main purpose of this fund is to host cultural visits by foreign dignitaries organize meetings/ conferences under the cultural agreements. | 6 CEPs were signed with the countries Belarus, Cyprus, Netherlands, China, Vietnam and Thailand | 0.01 | -- |  |
| (o) | Financial Assistance for Tribal/Folk Art | To promote and disseminate tribal art of culture. The scheme aims at creating awareness of richness of tribal /folk art through documentation and organizing cultural activities including festivals. | -- | 2.00 | About 600 organizations / individuals to be assisted. | 340-individuals/Voluntary organizations were given financial assistance during the year. | -- | 1.02 | Includes 20% provision for ST. |
| (p) | Financial Assistance for the Preservation & Development of cultural Heritage of the Himalayas | To promote, project and preserve the cultural heritage of Himalayas. | -- | 1.00 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 60 NGOs / individuals were given grant-in-aid | -- | 0.74 |  |
| (q) | Financial Assistance for the Preservation and Development of Buddhist/ Tibetan Organizations. | To promote and propagate the scientific development of Buddhist/ Tibetan culture and tradition and also research in the relative fields. | -- | 3.70 | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 63 organizations/ monasteries/ individuals were given financial assistance during period under the report. | -- | 3.90 |  |
| (r)* | Centenaries & Celebrations | To provide financial assistance to cultural organizations/NGOs for celebration of centenaries of renowned personalities of India. | 7.00 | -- | Depending upon the receipt of eligible applicants and subject to recommendation of the Expert Advisory Committee. | 48 NGOs/ organizations were given financial assistance for celebration of centenaries of the renowned personality. | 0.63 | -- |  |
| (s) | Maintenance of National Memorials | To commemorate the role of eminent National Personalities who have contributed to and played a historic role in the history of the country | 2.00 | -- | Financial assistance is given to the voluntary organizations for maintenance of National Memorials | 40 organizations including Ramana Maharishi Centre for Learning, Bangalore were given grant under the scheme. | 0.01 | -- |  |
| (t) | Building Grants to Cultural Organizations | To give grants to voluntary cultural organizations working in the field of dance, music, fine arts, indology and literature for construction of building and purchase of material. | -- | 7.00 | 400 beneficiaries will be awarded grants. | 225 NGOs provided grant for infrastructure facilities and also purchase of equipments in the field of art and culture | -- | 3.39 |  |
| (u) | Financial assistance to Cultural Organizations with a national presence | To provide assistance Institutions/Organizations engaged in cultural activity at the National level. | 1.95 | 3.80 | The grant will be given to the prominent institutions like R.K.Mission. INTACH and other organizations with the national presence. | R. K. Mission was given grants for Plan and Non Plan activities & INTACH and SPIC MACAY were given grants under Plan head. | 1.95 | 1.51 |  |
| (v) | Development of Cultural Organizations (scheme for research support to NGOs in cultural activities) | To give grants to voluntary organizations of national fame engaged in cultural activities for holding a conference, seminars and symposia on important cultural matters. | -- | 1.60 | Organizations to be awarded grants, as per the recommendations of the Expert Committee, as and when it meets during 2007-08. | 374 NGOs / individuals were benefited from the scheme in the period under review. | -- | 1.18 |  |
| (w) | Twang Monastery | To educate the monks and also act as a centre for Buddhist Cultural Studies. | -- | 0.01 | Monastery will continue its on going programmes. | Continued its on- going programmes on Buddhist studies. | -- | 0.41 |  |
| (x) | #### Tibet House, New Delhi | ## The main aims and objectives of the Tibet house are to promote, preserve and protect the Tibetan culture, encourage the exchange the ideas and techniques between Tibetan and non-Tibetan artists and craftsmen. | -- | 0.30 | Tibet House will continue to implement there on going programmes including maintenance of Museu | Continued its activities relating to programme coordination for awareness on Tibetan Buddhist Studies and Culture and also maintained its museum. | -- | 0.30 |  |
| (y) | #### Development of Jalianwala Bagh Memorial | ## In order to take up a comprehensive development of this Memorial, refitting its status and importance in the history of India freedom struggle. | -- | 0.50 | Developmental programme will be taken up to upgrade the Memorial. | JBM Trust carried out developmental activities spending Rs.0.48 crore during the year. | -- | 0.48 |  |
| (z) | #### Assistance for Preservation and Promotion of Intangible Heritage of Humanity. | ## To preserve and promote Kutiyattam, Ramlila and Vedic Chanting. | -- | 4.00 | About 200 organizations / individuals to be assisted. | 95-Cultural Voluntary Organizations/individuals were given financial assistance under the scheme. | -- | 1.53 |  |
| (aa) | #### Scheme for safeguarding and other protective measures in the area of Intangible Heritage and Cultural Diversity (arising out of UNESCO Convention) | ## In order to meet the obligations arising from the UNESCO conventions on the safeguarding of intangible cultural heritage and cultural diversity. | -- | 0.10 | A token provision has been made for the new scheme. | This scheme is still to be implemented | -- | 0.00 |  |
| (bb) | #### Awareness creation in the area of Intellectual Property Right (IPR) and Setting up of a National IPR Cell for Creative Artists and Artisans. | ## To protect the Intellectual Property Rights of Indian Artists. | -- | 0.10 | A token provision has been made for the new scheme. | This scheme will be initiated for implementation from the year 2008-09. | -- | 0.00 |  |
| (cc) | #### Plan scheme for promotion and dissemination of Awareness about Indian Culture and Heritage | ## To take up activities relating to promotion of cultural and heritage through performing arts and theatres. | -- | 0.50 | A token provision has been made for the new scheme. | This scheme will be initiated for implementation from the year 2008-09. | -- | 0.00 |  |
| (dd) | #### Cultural heritage volunteers (CHV) Schemes | ## To protect the young people from marginalization and neglect by ensuring their social inclusion and involvement in civic and cultural programmes. | -- | 0.20 | A token provision has been made for the new scheme. | This scheme will be initiated for implementation from the year 2008-09. | -- | 0.00 |  |
| (ee) | #### Pilot scheme for Cultural Industries | ## In order to convert wide variety of creative expressions, traditional designs and endless variety of crafts into cultural industries products. | -- | 0.50 | The scheme is to be implemented through ZCC on pilot basis. | This scheme will be initiated for implementation from the year 2008-09. | -- | 0.00 |  |
| (jj) | #### Centre for Management of Cultural Resources | ## To develop centre of Excellency for Research and Training in inter-disciplinary areas in an integrated manner so as to introduce capable managers and researchers for Cultural Resources. | -- | 0.05 | A token provision has been made. | This scheme will be initiated for implementation from the year 2008-09. | -- | 0.00 |  |
|  | Total (Promotion of Art and Culture) |  | 76.64 | 202.96 |  |  | 106.67 | 223.72 |  |
|  | Archaeology, Archives and Museums |  |  |  |  |  |  |  |  |
| 17 | Archaeological Survey of India | This organization is mainly involved in conservation, preservation and maintenance of the built heritage of the country. | 185.50 | 98.00 |  |  | 185.87 | 90.88 | * includes establishment / administrative expenses. |
| (i) | Conservation & Preservation of Ancient Monuments: its up keeps and maintenance including environmental development. | For conservation, preservation and maintenance of centrally protected ancient monuments and sites. |  |  | Conservation works at about 800 monuments which includes structural conservation, horticultural development of 150 centrally protected monuments and upgradation of science laboratory at Dehradun and set up of research/ conservation laboratory at Aurangabad. | 1500 works were taken up, of which 600 completed in the year 2007-08. More than 800 monuments have been taken up for conservation and structural repairs, chemical preservation and environmental development, besides day-to-day maintenance of centrally protected monuments. This also includes monuments in North-East States. |  |  | Natural calamities. |
| (ii) | Providing basic amenities tourists | Development of basic amenities in Ancient monuments including provision of toilets, drinking water facilities etc. |  |  | Better visitors’ facilities and other amenities in all World Heritage Monuments and sites. | Better visitor’s facilities were provided in the various monuments/sites including World Heritage Monuments/Sites |  |  |  |
| (iii) | Excavation and Exploration. | Archaeological Exploration Scientific clearance and Marine Archaeological Explorations. |  |  | The projects include archaeological investigation using modern scientific methods, analysis of archaeological samples and artifacts, creation of systematic storage spaces for artifacts and potteries retrieved from exploration & excavation, establishment of new Excavation Branch for North East States and activities of Under Water Archaeology, etc. | ASI carried out the excavations at Barabati Fort complex, Juafardin, district Nalanad, Bihar, Bangarh, district South Dinajpur, West Bengal, Salvankuppam, district Kanchipuram, Tamil Daulatabad, district Aurangabad, Maharashtra, forecourt of Dwarkadheesh. |  |  |  |
| (iv) | Development of the Archaeological Site Museums. | Maintenance and Development of Site Museums at various archaeological sites and monuments. |  |  | Up gradation/ Modernisation, security up gradation, documentation and museum catalogue of 41 site museum and proposal to open 3 new museums. | 42 museums are managed by the respective Circles of the ASI. A new archaeological museum at the Harappan Site, Dholavira was opened. Work on two other museums is in progress at Deeg Palace, Bharatpur, Rajasthan and Ftehpur Sikri, Agra. Construction of new museum buildings at Chanderi and Khajuraho has been completed. The construction of a new museum building at Shivpur is near completion. Holistic upgradation and modernization of museums has been taken up at Hampi; Nagarjunakonda; Srirangapattanam; Fort St. George, Chennai; Mattancherry Palace, Kochi; Velha Goa; etc. |  |  |  |
| (v) | National Mission for Ancient Monuments and Antiquities | Inventorisation of unprotected monuments and antiquities. Creation of awareness. Preservation and conservation of unprotected built heritage and antiquities. |  |  | (i) Preparation, documentation of a data base of unprotected monuments and another for antiquities. (ii) Conducting of workshops for awareness and training programmes for stake holders. | (i) Template for documentation of antiquities finalized. Template for Monuments’ data base will be finalized by March, 2008. (ii) Capacity building and awareness creation activities will be undertaken in the remaining 4 years of the Mission. |  |  | Reasons for non-achievement: (i) Initial year of the Mission. Preparatory steps took much longer than expected. (ii) Manpower not in place. (iii) Involvement of State Governments is essential for which constitution of State Level Implementation Committees has been initiated. |
| (vi) | Publications | 1.Publications under Academic and Informative Series. 2.Dissemination of knowledge and awareness generation regarding heritage. |  |  | Academic 1. Memoirs – one issue. Informative 2. Guide Books (WHS) – 4. 3. Guide Books other than WHS( reprint) – 2. 4. Brochures – 2. 5. Monograph on Conservation of Ta-Prohm (under Special Publication) | 1. Published 2. 3 Guide Books published. 1 will be published by March, 2008. 3. 1 Published. 1 will published by March, 2008. 4. Published. 5. Published. 6. Digitization – Proposed to be completed in 2008-2009 |  |  |  |
| (vii) | Administrative Expenses for Directorate & Sub-Offices | Payment of salaries, etc. of the staff |  |  | Payment of salaries, etc. of the staff & other administrative expenditure. |  |  |  |  |
| 18 | National Archives of India | The custodian of non-current records of enduring value of Central Government Ministries / Departments / Offices and their predecessor bodies. The nodal agency for record management activities and their permanent preservation and use by the posterity. | 12.24 | 4.00 |  |  | 10.65 | 1.91 |  |
| (i) | Expansion of records Management Programme | i. Acquisition of Public Records ii. Appraisal of files iii. Vetting of Records Retention Schedule. iv. Holding of Meeting of Archival Advisory Board v. Compilation of 9th and 10th Report of DGA on Implementation of Public Records Act 1993. vi) Organizing Orientation course in RM for DROs. vii. Inspection of DRR’s of Ministry/ Departments/ Offices. |  |  | Acquisition of 25,000 files. Appraisal of 2500 files Vetting of 15 records 7 orientation courses to be conducted. Inspection of 12 developmental record’s room. | 23,911 files from various Ministries/ Department were acquired. 12341 files appraised 10 retention Schedules vetted 7 courses conducted 12 Departmental Record Rooms inspected |  |  |  |
| (ii) | Expansion of repair and reprography | Repair of records, binding of books/ volumes/ preparation of security Microfilming, Preparation of Security Microfiche films, Positive printing of microfilms, Supply of copies (Xerox/ Photo/ Reader/ Microfilm to scholars as per their demand). Out sourcing of negative and positive microfilming/ out sourcing of positing microfilming of negative microfilm rolls available in NAI. |  |  | 1,18,000 sheets to be repaired, 4000 books/ volumes to be bound, 720 rolls to be microfilmed, 60,000 exospores to be completed, 28,000 meters printing to be done. 50,000 copies to be supplied to scholars, 44,35,200 pages approximately (3168 microfilm rolls) & positive copy of 3168 master negative rolls. 7920 rolls to be completed. | 112108 sheets repaired; 157 Volumes, 1171 books, 3422 misc. items bound; 216 volumes,175 books 5129 misc. items stitched; renovation work is in progress under CRL; 582 rolls microfilm, 42500 Exposures of Microfiche film completed;34240 mts of positive print done; 97609 copies supplied to scholars. Under digitization 14959 images prepared under scanning, 5100 images prepared under microfilm scanner. |  |  |  |
| (iii) | Expansion of library and administration | Purchase of books Data Entry in to the computer Preparation of data input sheets. |  |  | 600 books to be purchased. 700 books to be made. 700 sheets. | BAC meeting was held on 15 June, 2007. 740 books/ periodicals accessioned.24 data entries were completed. 700 input sheets were prepared. 834 books cards prepared, Other ongoing programmes in the Archival Library continued |  | By holding BAC meeting by the departmental experts and approval of Ministry of Culture. |  |
| (iv) | Expansion of School of Archival Studies | - One Year Diploma Course in Archives and Record Management – 2006-07 and 2007-08 - Short Term Courses in Archival Management and allied disciplines. |  |  | (a) One year diploma course 2006-07 to be completed and one year diploma course 2007-08 to be commenced and continued . a. Short Term Course in Record Management-two courses to be conducted. b. Reprography - (two courses). c. Servicing and Repair of Records (two courses). d. Care and Conservation of Books/ MSS/ Archives- (two courses). e. Archives Management- (one course). | One year diploma course in Archives and Record Management 2006-07 completed, whereas Diploma course for 2007-08 started. 65th and 66th sessions of the short term course in Records Management conducted 55th & 56th sessions of the course in Reprography were conducted 56th & 57th sessions of the course conducted 65th 66th sessions of the course conducted 1 seminar and 5 workshop conducted by NAI. |  |  |  |
| (v) | Listing of records ref. Media including computerization of records | Listing of private papers. Listing of oriental records and preparation of catalogue/ reference cards of acquired documents. Data Entry of reference media of 25 lakh records in NAI by out sourcing. Upgradation of AIMS Software by NIC. |  |  | 5000 items of private papers to be listed 1680 items to be descriptively listed. After approval of competent authority the project of Data Entry of Reference Media of 25 lakh records in NAI has been awarded to M/S Micrografics India, New Delhi. Upgradation of AIMS Software. | 155 items were descriptively listed, arranged 5400 documents, 4646 items/ letters of K.M. Munshi Papers, Kastur Bhai and Lal Bhai and N. Sanjiva Reddy Papers were subject listed. Data entry of 504355 of records were completed by M/s Micrographics India New Delhi. Data entry of Pvt. Archives, oriental records, cartography etc. is being continued. |  |  |  |
| (vi) | Setting up of a Record Centre in Eastern Zone | - Survey and Accession of non current records - Appraisal of Records - Vetting of records retention schedule |  |  | - Survey and acquisition of non current records of central Government Offices located in North Eastern Zone. - 2000 files to be appraised - Vetting of 2 record retention schedule | 53 volumes of papers manuscripts from the Orissa Research Project, Heidelberg University 12 files (1914-64) were received from GOI 4227 files appraised 2 schedules vetted. |  |  |  |
| (vii) | Scheme of financial assistance for preservation of manuscripts/ rare books to NGOs. | Grants – Committee Meeting. |  |  | One Grants Committee Meeting to be held and the amount recommended by the Committee to be released to the recommended Institutions. | 62 NGOs were sanctioned grants amounting to Rs.31.31 lakh during the year. |  |  |  |
| (viii) | Scheme of financial assistance to State/ Union Territory Archival repositories and Museums. | Grants Committee Meeting. |  |  | One Grants Committee Meeting to be held and the amount recommended by the Committee to be released to the State Archives, Government Libraries/ Museums as recommended. | 17 Organizations were sanctioned grant amounting to Rs.23.87 lakh. |  |  |  |
| 19 | National Museum | A premiere institution in the field of art and culture in India and involved in important work of acquisition, conservation, exhibition and educational activities | 8.04 | 10.00 |  |  | 5.06 | 5.96 |  |
| (i) | Photo-documentation of art objects and events | Coloured photo documentation of Museum’s collection, exhibits for exhibitions and publication purposes and events for publicity purposes, done as per demands. - Miniature paintings - Central Asian antiquities - Manuscripts |  |  | A. Photo documentation of Paintings, Harappan objects, Manuscripts, Jewelry, Bronzes exhibits & Gupta exhibits etc. B. Photo documentation of Art objects and events is a continuous work of museum collections and events.` | 2888 black and white prints including enlargements and 809 B&W negatives were prepared,10930 colour prints and 6325 (35mm) colour negative prepared. 997 colour slide also prepared, museum artifacts documented before and after conservation treatment, 782 B&W prints & 663 negatives prepared |  |  |  |
| (ii) | Display & modernization of Museum - reorganization of existing galleries. | To keep the galleries and display of objects therein as per the international practice and modern technology. |  |  | - Modernization work carried forward from the previous year i.e. Jewellery Gallery, Central Asian Wall painting gallery, Pre Columbian and Western Art Gallery, Decorative Art Gallery and Maritime Heritage Gallery. - Installation of Modern gadgets such as Plasma Screen, Kiosks etc. in selected galleries. - Design of Key Gallery including the Foyer, Reception entrance to the Library and Auditorium. | Display of Early Man Gallery, Upgradation of Harappan gallery, Manuscripts, Central Asian antiquities, Bronze Gallery, Kushana-Ikshvaku Galleries, Textiles Gallery, Decorative Arts, Tanjore Gallary and Pre-Columbian & Western Arts. |  |  |  |
| (iii) | Reorganization of Reserve Stores | To keep the galleries and display of objects therein as per the international practice and modern technology. |  |  | - Central Asian Antiquities - Textiles Modular storage - Decorative Art: Special storage for wooden door collection. - Anthropology - Pre-Columbian & western Arts | This is continuing work and is under progress. |  |  |  |
| (iv) | Restoration and Conservation of art objects. Restoration of Oil Paintings / Conservation of antiquities / art objects / training course in conservation, Acquisition of equipments for conservation / binding of manuscripts. | - To protect the antiquities and art objects from decay. - To train the Museum staff of National Museum and other museums/Institutions in latest technology in conservation. - To keep laboratory well equipped with the latest equipments. |  |  | - Treatment artifacts of National Museum - Treatment & display of Central Asian Antiquities. - Conservation of manuscripts - Treatment of MSS, Central Asian Antiquities and Tribal Art artifacts. - Conservation of art objects using 3D digitization technology. - 3 months training course of paintings - Programme on preventive conservation for curators of different Museum/ Art Galleries (four days) - Teaching & conducting of practical class programme for students of NMI - Treatment of Paintings of Shri Chitra Art Gallery, Thirvananthapuram Treatment of Paintings of North Block/ Parliament House. | 415 artifacts cleaned and preserved, conservation of 22 oil paintings of Ashoka Hall Rashapati Bhawan and 42 oil paintings conserved at Shrichitra Art Gallery, Trivendrum, 308 historical document of belonging to Cabinet Secretariat restored, 2 oil paintings of M/o Agriculture treated and restored, chemical treatment of 1000 objects, 150 mss conserved, restoration of 100 illustrated mss, chemical analysis of 200 Harappan Metallic objects. |  |  |  |
| (v) | Exhibition | - To popularize the ancient Indian Art & Culture. - To organize thematic exhibitions. - To organize exhibitions under Cultural Exchange Programme |  |  | Exhibitions to be sent abroad - Exhibition entitled “Gupta Art” to be organized in France. - An exhibition to be organized in Singapore & USA. - The work of organizing Nizam Jewellery is under progress. | Exhibition organized in India Conservation of Mural Paintings in Ajanta Caves, Dressing like Gods, Nizam’s Jewellery, 11 Exhibitions held under CEP&, prepared reports of no. of exhibits sent abroad for the Gupta Art exhibition held at Paris. France, Beauty in Asia exhibition at Singapore and Arts of Kashmir, at New York |  |  |  |
| (vi) | Strengthening of Museum Security | To keep security arrangements up-to-date keeping in view the changing threat perceptions. - To keep the Museum and antiquities from threats such as fire etc. |  |  | - Installation of barbed wire around the boundary of National Museum - Conversion of black & white CCTV cameras into coloured ones - Extension of CCTV coverage to remaining galleries & storage area - Procurement of Thermal Surveillance cameras - Perimeter IR Detection System - Procurement of Perimeter fence (Electric) Procurement of Real time DVRs, in CCTV Control Rooms. | The work of installation of C-Cure Security system was completed by ECIL. Installation of Security Gadgets, Extension of CCTV coverage to uncovered areas. |  |  |  |
| 20 | National Council of Science Museums | To popularize Science and Technology by organizing exhibition, seminars, training programmes for Science Teachers, students, young entrepreneurs, technicians etc. | 16.40 | 17.00 |  |  | 16.40 | 20.03 |  |
| (i) | Setting up of new galleries, upgradation and updation of exhibits, new circulating exhibitions, new mobile science exhibition units, new training facilities, educational programmes, strengthening of infrastructure and existing facilities of 27 science centers located at various parts of the country. | To modernize, upgrade and popularize the science and technology in the country. |  |  | SRSC Solapur, Gangtok and new wing “The planet We live In” at Science City, Kolkata. Régional Science Centre Raipur, Ranchi & Dharwad New Galleries on “Bio-machine” at RSC, Guwahati, ‘Energy” at RSC Bhopal, “Information & Communication Technology” at RSC Nagpur. Gallery on “Poular Science” at DSC Dharampur & “Heritage” gallery at NSC, Delhi, KPSC Kurukshetra, “Electro Technique” gallery at VITM Bangalore, “Colamine” & “Transport” gallery Kolkata,”Fludics” gallery RSC Lucknow. Gallery on “Human Biology” at NSC Delhi Travelling Exhibitions on “Biodiversity” ,“Nanotechnology”, “Illusion”, “Human Genome” “An eye in the Sky”, “ The World of Astronomical Observatories” and “ A Century of Physics”. Two new exhibitions | TV Gallery at BITM was inaugurated on May 2, 2007 whereas work for Transport Gallery in progress. Gallery for SRSC Gangtok will be completed. Work for Human Performance at DSC Burdwan is in progress. Gallery on ‘Energy’ to be set up at RSC Bhopal, Gallery on ‘Electro technique’ at VITM under progress. Nanotechnology at VITM is in progress, work for gallery at RSC Dharwad is in progress, Emerging Technologies gallery at RSC, Tirupati was inaugurated on Aug 18, 2007, Popular Science gallery at RSC, Tirupati and at DSC Gulbarga are in progress; ‘Heritage’ at NSC, Delhi will be completed whereas ‘Human Biology’ gallery will be extended at NSC Delhi.; ’Fluidics’ gallery at RSC, Lucknow will be completed. Renovation of ‘Heritage’ galley at KPSC, Kurukshetra to be completed. Information and Communication Technology at RSC Nagpur, Virtual Reality Corner at GSC, Panjim, have been completed/ inaugurated. Emerging Technologies gallery at NSC Delhi inaugurated on 31.07.2007, Wonder World of Materials at RSC Lucknow is in progress. Galleries on Popular Science and Communication at BITM are in progress. |  |  |  |
| (ii) | Centralized procurement of LFFP system and Other Major equipment. | To set up large format film projection system at NSC, Mumbai. Procurement of high resolution 3D film and Motion simulator. |  |  | Addition of new facility by setting up of LFFP system at NSC, Mumbai to offer immerse science-learning ambience. | Image Processing Units for Virtual Reality Exhibit and Projection Equipment have been ordered for their procurement. |  |  |  |
| (iii) | On going new projects – KCMP, Kurukshetra | To set up Kalpana Chawla Memorial Planetarium at Kurukshetra |  |  | Being the first planetarium of its kind, being set up in the state of Haryana, this Planetarium is expected to provide astronomy education to the visitors. | The project has been completed and handed over to state authority on 12.07.07. This was inaugurated on 24.07.2007. |  |  |  |
| 21 | Science Cities | To popularize Science and Technology at selected centers in the country. | -- | 13.00 |  |  | -- | 10.39 |  |
| (i) | To establish Gujarat Science City at Ahmedabad | To inculcate scientific temper in public at large and students in particular. |  |  | Facilities like Imax Theatre, Musical Fountain, Hall of Science, Energy Park, Simulator, Amphitheater are operationalised and Space and Communication Pavilion, Life Science Park, Children Activity Corner will be opened to public. | March 08, about 7.00 lakh visitors visited the Science City and took part its various scientific programmes and activities in the lush green campus. |  |  |  |
| (ii) | Setting up of Pushpa Gujaral Science City, Kapurthala, Punjab. | To popularize science& Technology in the State and adjoining areas by inculcating scientific temper in public at large and students. |  |  | Construction of : - Exhibitions Galleries(4) - Convention Hall - Yard toilet - Boating Office & Shelter - Administrative Building - Evolution Gallery Galleries Under Development: - Energy Park - Evolution Gallery( Dinosaurs Park) - Digital Planetarium - Upgradation of space Gallery Upgradation of health and Biotechnology | Civil & electrical work completed. External works is in progress. Construction Completed. Completed. Completed. 85% Completed. Work in progres Completed 95% Completed. Work in progress Work in progress |  |  |  |
| (iii) | New Projects: RSC Raipur, Ranchi Dharwad, ## SRSC Solapur and Kalimpong, Science City/Centre at Mangalore. | To popularize science and to spread science message and to create a scientific temper and awareness among the people of the region. |  |  | To set up new centers in the state of Chattisgarh, Jharkhand, Karnataka, Maharashtra and West Bengal. | Foundation work already completed super structured work is going on. And project will be completed in December, 2009. Construction of main building work is going on and project is likely completed by Dec. 2009. Architectural plan of the main building is ready tenders has also been floated Construction work is incompletion stage and will likely to be completed in 2008-09. Center was handed over to local authority on 11.09.2007 |  |  |  |
| 22 | Anthropological Survey of India | Committed to research activities on human population from bio-culture perspectives. Its activities include collection, preservation, maintenance, documentation and study of ethnographic materials as well as of ancient human skeletal remains. | 11.20 | 6.50 |  |  | 10.72 | 7.21 |  |
| (i) | Documentation and Dissemination | To maintain Anthropological Libraries in 7 Regional Centres and Central National Library at Kolkata. At present Survey possesses museum artifacts stored in all the seven zonal museums and central museum at Kolkata. During the current financial year it is proposed to initiate conservation & documentation of all these specimens with scientific methods by trained manpower. All the documentary films possessed by Survey to be converted to Beta-com will be completed. All silent films will be edited for voice and sound mixing. Production of new documentary films will be taken up on specific themes like 1. Children of Forest Jenukurumba 2. Village life in North Karnataka 3.Transhumans in Western Himalayas 4.Ghotul-The Kingdom of the young 5. Memorial pillaras of Bastar 6. Jarwa Life 7. Any specific films recommended by government. |  |  | Libraries of the Survey being center of excellence in the field of Anthropological research all over the country, through which around 1000 researchers, professors, administrators of different academic and other organizations take the help from this library as a centre of reference and documentation. More than 2,00,000 visitors including scholars, students and common man and dignitaries will visit anthropological museums. Survey has 25 16mm visual documentary films and more than 1,000 audio-cassettes. Steps have been taken by signing MOU with Film Institute for archiving the 16mm films and transforming them to Beta-cam to make DVDs and CDs. | Research Scholars of the survey carried out the documentation work of important cultural events called ‘Sakewa’ observed by the Nepali communities. Refresher Course on Care of Mueum objects with special reference of manuscripts conducted in the chemical conservation & research laboratory, govt. Museum Chennai. The Survey participated in 2 local exhibitions viz. Basirhat Kala-O-vijnan Utsav &Pashim Banga Vigyan Mancha. |  |  | Work of conversion of documentary films possessed by this survey to Beta-Cam format is under process. The survey takes active initiative to organize exhibition on Human origins and Genome & People of India. Modernization of all the survey’s libraries continues. Regarding modernization of libraries in the survey, , retro-conversion and digitization of all the libraries in the survey is in active process. |
| (ii) | Book Exhibitions/Fair | For promotion and dissemination of ethnographic materials as well as of ancient human skeletal remains and research carried out thereon. |  |  | Survey participates in several exhibitions organized by local authorities at Kolkata, including National book exhibition. In order to hold exhibitions at several places in Kolkata, where there is a continuous demand, survey proposes procurement of a specially built mobile van during the year. | The survey participated in several exhibitions organized by the local authority at Kolkata including national book exhibition |  |  |  |
| (iii) | Fellowship programme | The Survey proposes to revise the stipend of the fellows at par with the National Organizations like UGC, ICMR etc. since the fellowships that are offered are very meager and in terms of qualified manpower is inhuman. |  |  | Fellowships are an important component of manpower development as a resource in the country. At present the Survey has 47 fellows. It is proposed to enhance total fellowships to 67 and also increase the stipend. | Initiative for walking in interview for selection of research fellow in different categories was held on 18.06.2007. | It is a continuous process. |  | The deployed research fellows are already engaged in field work for various national plan projects of this survey. |
| (iv) | Induction of DNA technology | Maintenance of Infrastructure already developed at Kolkata, Mysore, Nagpur, Shillong and Port Blair. Procurement of Liquid Handling Systems at Mysore. Development of laboratory facilities with DNA technology up to PCR level and DNA Banking at Dehradun and Udaipur. Augmentation of DNA Banking facilities at all the regional centers including headquarters. Establishment of core Phenotypic facility at Kolkata and Mysore in terms of High Through put automated bio-chemical analyzers. A concerted effort to induct tissue culture technology for cell lines. |  |  | At the moment survey can boast of creating state-of-the-art advanced facilities, which are all functional, in 5 of its centers. The infrastructure development is planned in such a way that manpower training is also quite in place, by the time technology is inducted in survey. Now survey is poised to implement national programs concerning ‘genetics and health’ integrated with cultural practices of communities. | Annual maintenance of inducted lab equipments in the DNA labs at Nagpur, Mysore, Shillong and Kolkata continued, DNA lab of A&N regional centre, Port Blair was inaugurated on 22.10.07. One -86 degree deep freezer installed for DNA lab of Andaman & Nicobar Regional Centre, Prot Blair. |  |  |  |
| (v) | DNA Polymorphism of the Contemporary Indian Populations & Ancient Skeletal Material | Human Genome Diversity Analysis: 1) 27 populations Y SNP, Y and autosomal STRs. 2) Collection of blood samples from populations in north-east and other parts in India. 2) Candidate gene polymorphism of diseases in patient and population cohorts. |  |  | Baseline information that is being generated on Indian populations in terms of human genome diversity will be useful in medical applications | Research scholars of this survey carried out fieldwork in the West Kameng district of Arunachal Pradesh to collect blood samples and research data among the tribe ‘Ak/Miji under this project. Procurement of consumables for lab analysis continued. Analysis of DNA sequencing is in progress |  |  | A research paper on mtDNA sequencing has been accepted in American Journal of Physical Anthropology. Initiatives have been taken for field work to collect blood sample from scheduled communities. |
| (vi) | Growth (reoriented as children in N.E. : Growth and Development Study – A Public Health issue) | To generate information about the health status of the children of the North East India in Particular |  |  | Growth of children as public health issue is a mission mode project in north-east. | Computerization and analysis of Data collected from field continued. |  |  | Deployed research scholars along with fellows continued field work. |
| (vii) | Narmada Valley Excavation | The extensive excavation in Narmada Valley in search of Palaeo-anthropological materials, before submergence. |  |  | Field explorations will be continued in Narmada with the possibility of undertaking excavations as a collaborative program with ASI. Similar sites in the other parts of the country will be explored. The proposal to collaborate with European and African groups with extra mural funding will be further pursued. | Analytical research of the collected fossils from the Narmada river-bed continued in Palaeo-anthropological Laboratory. 6 research scholars proceeded on 3 months tour for carrying out exploration cum trial excavation at Hathnora. |  |  |  |
|  | NEW SCHEMES 1. People of India: Cultural Diversity (Five components) | a) Intangible & Tangible Cultural Heritage: Oral Traditions, Folk Taxonomies, Social Structure & Bio-cultural Adaptations with Gender Perspectives. b) Establishing a National Centre for Community Knowledge at the new building at Udaipur. c) National Centre for Visual Anthropology: Kolkata d) Man & Environment e) Bio-cultural Linkages with border area countries. |  |  | a) Cultural Diversity of the people of India need to be scientifically documented and projected for greater harmony among the communities. The issues that are addressed are contexualization of ‘Traditional Knowledge’ and linkages of cultural diversity with bio-diversity in the context of ‘man and environment’. Besides, understanding the bio-cultural linkages with border area neighbouring countries is an urgent issue in view of globalization and merging of borders, and state sovereignty. Formulation of programme, area of studies through workshops and initiation of first phase of fieldwork by the deployed scholars among the SC/ST communities b) Establishment of ‘National Center for Community Knowledge ‘ at Udaipur and a center of excellence for ’visual anthropology’ will be tangible outcome of the scheme. Initiation of establishing the centre and to procure equipments for digitisation work for broader highlighting of the intangible cultural heritage of Western India. c)Initiation of establishing the centre for visual anthropology in the new building of the Head Office of the Survey in Kolkata. d) This project is earmarked for SC/ST, which requires extensive fieldwork to frame the All India schedule during the year. e) Reconnoiter tour for collection of first hand information for executing the project will be conducted during the first year of annual plan period. | a) After completing pilot survey by the deployed research scholars in different eco-cultural zone, they engaged in finalizing the programme of field work. Engagement manpower of contract is under process b) Layout plan & concept document for developing the design of establishing a National Centre for Community Knowledge at Udiapur is under process c) The survey organized training course on usual anthropology for its 22 officers and staff from 29 May 17th June 07. Deployed personal taking initiative for formulation of schedule/programme. d) workshop on "Simlipal Biosphere Reserve and "Khangchendoznga Biosphere Reserve" organized by the survey at Bhuwaneshwar and Gangtok for the deployed research scholars. Another workshop on the new biosphere project Achanakmar – Amarkantak Biosphere Reserve held at Nagpur on 25.09.07 for the research scholars. e) Initiative to formulate the programmes schedules are in progress. |  |  |  |
|  | # 2. Bio-cultural Adaptations (Two components) | a) Community Genetics and Health in North – East India b) Genetics & Health: Family Study |  |  | a) In this program we would like to initiate a collaborative program in North-East on the issue of G6PD deficiency and hemoglobinopathies. b) Bio-cultural risk factors for life style diseases need to be evaluated/ discovered by the analysis of several quantitative factors (genome/cultural/environmental) within families. It is proposed to initiate a well designed study at Mysore, which will be implemented with a consortium of specialties and will be known as ‘Mysore Family Study’ | Formulation of programme schedule, deployment of scholars to initiate a collaborative program in NE is in progress. Procurement of consumables, regents, chemicals etc. for the lab. The deployed research scholars are engaging in reconnoiter survey. |  |  |  |
| 23 | Nehru Memorial Museum and Library | Responsible for collection of books, newspapers, unpublished references, private papers/ photographs film takes, and also translation of important papers relating to Pundit Jawaharlal Nehru. | 5.90 | 3.50 |  |  | 6.70 | 22.45# | # Rs. 20.00 crore provided for development and modernization of NMML, in accordance with the FM's Budget Speech |
| (i) | Promotion of Research/ Award of Fellowships. | To offer three level of fellowships namely Senior Fellowship, Fellowships and Junior Fellowships and to institute, award scholarships and monitory assistance. |  |  | Working on different research projects and the findings of the fellows/ research papers created by them are being published in the form of monographs. | Fellows were working on different research projects, and its findings and research papers created by them being published in the form of monographs. The final manuscripts submitted by the fellows are published in book. |  |  |  |
| (ii) | Publication Programme | To undertake to promote publication of books, monographs, periodicals and papers incorporating the research of the studies carried out at the NMML. |  |  | Apart from bringing out the quarterly journals, NMML as also publishing the monographs created by the fellows of the NMML. A project has also been taken up to publish the selected writings of C. Rajagopalachari. | Published monographs created by the fellows and also brought out quarterly journal. Publishing of selected writings of C. Rajagopalachari have been undertaken. |  |  |  |
| (iii) | Seminars and Lectures | To organize lectures, seminars, symposia and conferences to promote and encourage the study of Modern Indian History. |  |  | Proposing to organize four seminars two at the national level and another two at the international level. Tuesday seminars and other lectures will also be organized as usual. | Organized 4 seminars, 2 at national level and another 2 at international level. Tuesday seminars and other lectures were organized. |  |  |  |
| (iv) | Development of Library a) Acquisition of books, Periodicals/ Resource Material a) Acquisition of book Racks & Library furniture c) Moderanisation of Library with the state of the art knowledge management facility | To maintain a Library of books, pamphlets, newspapers, periodicals, microfilms, still photographs, motions pictures, sound recording and other materials bearing on the History of Modern India with special reference to the Freedom Movement. |  |  | The Library will continue to acquire books, with a focus on Modern Indian History and related Social Sciences in addition to material on microfilm and photographs. The Library will be provided with the state- of- the- art facilities like digital membership, wireless Lan, Highend computer storage facilities for digital materials and the seminar room will be fitted with modern projection systems. | Library continued to acquire books on Modern Indian History and related to Social Sciences. It provided with the state of Art facilities like digital membership, wireless LAN, High end computer storage facilities for digital materials. |  |  |  |
| (v) | Nehru Planetarium Activities | We have taken over the Nehru Planetarium in August 2005. This is the only planetarium in the Capital and its programmes stimulate scientific interest among the children. |  |  | We proposed to modernize the Planetarium. A new laser based planetarium equipment will be installed as present machine is very old. Also many competitions to popularize science will be conducted. The exhibition area will also be renovated. | To modernize planetarium installed a new laser based planetarium equipment and the exhibition area partly renovated. |  |  |  |
| 24 | Indian Museum, Kolkata | Engaged in reorganization and renovation of galleries housing unique treasures of Indian and foreign art representing centuries of cultural ethos and tradition. | ###### 4.40 | ###### 8.50 |  |  | 2.49 | 3.97 |  |
| (i) | Modernization, development, renovation and upkeep of galleries of art, Archaeology, and Anthropology Sections | The objectives include refurbishing, modernization & renovation of different galleries and reserve collections with updated arrangements and techniques. |  |  | i) Reconstruction, renovation of 18 galleries ii) Setting up of new 4 galleries - residual work - iii) Intercom facility – 1 case iv) Equipment purchase – 3 cases v) Electrification of go-down – 1 case vi) Showcase – redesigning – 1 case vii) Air-conditioning of gallery – 3 nos | Development and upkeep galleries is in progress with regard to Long Arch. Gallery , Decorative Art & Textile gallery, Long Art gallery consisting of Textile & Decorative Art, Painting Gallery, Bronze gallery, Anth. Gallery etc. |  |  |  |
| (ii) | Strengthening and modernization of security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. | To strengthen the security arrangements in the galleries, auditorium & Exhibition Hall, Buildings, Campus area etc. |  |  | i) Engagement of Security Agency & State Armed Police throughout the year. ii) Replacement of existing fittings, fixtures etc. - 10 nos. iii) Maintenance & purchase of upgraded & sophisticated security gadgets – 18 nos. iv) Illumination development of total campus area v) Upkeep of different electronic devices/fire/ burglary alarm, door frame and hand set metal detectors, CCTV etc. – 125 nos. vi) Purchase of computer -1 no. vii) Organization of training – 4 prog. viii) Construction of water tank– 1 scheme ix) Intermittent test of security system – 10 nos. - x) purchase of vehicle – 1 no. | Engagement of Armed Police Guard of the State Govt., security personnal engaged for deployment in the galleries from Pvt. Agencies, maintenance of CCTV installed at different galleries and exhibitions hall, etc. were provided during the year. |  |  |  |
| (iii) | Strengthening and modernization of Conservation Unit (Conservation Laboratory) | Scientific preservation of antiquities and restoration of art objects. |  |  | i) Conservation of sensitive materials – Textile, ivory, wood carvings, paintings, metal, stone, delicate artifacts etc. ii) Reorganization of mobile conservation Laboratory & its workshop; iii) Purchase of sophisticated instruments and equipments; iv) Reorganization of different laboratories (organic/ inorganic) v) Computerized documentation of conservation work; vi) Organization of refresher training courses on conservation, orientation course for museology students; vii) Organization of a Special long term project of laser conservation. | Conservation work has been done throughout the year. Upkeep and maintenance of laboratory and equipment was also taken care of. |  |  |  |
| (iv) | Programme of Education and Mass Communication Cultural Activities | Organisation of education activities and training programmes holding of temporary/ special & inter-state, in-house exhibitions, outreach programme through Museum on wheels (Museo Bus), organization of National/ International seminar and workshop. |  |  | i) National / International seminars and workshop; ii) Mobile exhibition, temporary exhibition; iii) Mass Communication Cultural programme; iv) Annual and memorial lecture series; v) Training programmes – In-service training course and short course in museum studies, practical aspects of Museum methods etc. | Execution of programme was performed on the basis of requirement. |  |  |  |
| (v) | Reorganization of Scientific galleries (Zoology, Geology and Botany) - | To raise the standard of display and presentation of the scientific galleries and to bring them at level with that of the cultural galleries museum proposes to renovate and update the scientific galleries also with the expertise of the respective Surveys. |  |  | i) Organization of the Gemmology Section ii) Extensive renovation of the Meteorite Gallery iii) Extensive renovation of the Mammal Gallery iv) Reorganization of the Insect Gallery v) Air-conditioning of Bird Gallery. | Zoological galleries present stuffed specimens as well as models of birds, reptiles, amphibians, mammals, fish, insects etc. Botanical section highlight one gallery of the economic aspects of plant where specimens of medicinal plants, jute, tea, rubber etc. & process of extracting products have been demonstrated with the help of models and charts. |  |  |  |
| (vi) | Physical verification of Art objects | Physical Verification of Art objects (Art, Archaeology & anthropology) by the Hon’ble Member of Physical Verification Committee. |  |  | Physical Verification to be conducted in respect of all objects/ artifacts as per recommendation of Physical Verification Committee. | i)Physically verified 14867of Archaeological objects and 7158 Coins, ii)3622 objects of Anthro. Section were physically verified. iii)6977 of art objects were physically verified. |  |  |  |
| 25 | Salar Jung Museum, Hyderabad | A museum of national importance houses rare and varied art collection from all over the globe acquired by Salar Jung I, II and III. | ###### 4.70 | ###### 7.50 |  |  | 4.74 | 6.96 |  |
| (i) | Project Building | Construction of additional floor over Western Block for expansion of Galleries. |  |  | Construction of fire pump & generator rooms, restoration/ improvement to auditorium, replacement of existing wiring, construction of store room etc. | All works listed in column 5 were completed during the year |  |  |  |
| (ii) | Developmental works (Existing Building) | Under taking various developmental works of the existing building including reorganization of Galleries, modernization of stores, conservation of manuscripts, library etc. |  |  | - Replacement of flooring in verandas of first floor of main building. - Construction of compound wall. - Replacement of chokes with electronic ballasts. - Replacement of existing wiring in the galleries. - Supply, installation testing and commissioning of 120 TR chiller plant including dusting and control panel. - Construction of 2nd floor of CISF Barracks. - Roofing with checkered tiles for Courtyard of Central foyer. - Re-organisation of modern paintings, Founder’s Children Section, Ivory, Miniature, Rosary and walking sticks galleries including improvements to existing galleries. - Modernization of two stores. | All works indicated in col.5 were completed. |  |  |  |
| (iii) | Upgradation of security | The security in the Museum is being upgraded by providing CCTV cameras, fire alarm system and fire hydrant system. |  |  | Amount required for upgradation of security of the museum for which the process has begun during previous year. | The work is near completion. |  |  |  |
| 26 | Indira Gandhi Rashtriya Manav Sangrahalaya, Bhopal | A museum conceived as a growing movement to depict the story of human kind in time and space highlighting human biological and cultural evolution | ###### 1.90 | ###### 5.00 |  |  | 2.00 | 5.20 |  |
| (i) | Maintenance and strengthening of indoor museum with extensive galleries. | Develop infrastructure facilities for achieving the objectives of documentation, display and dissemination of rich and diverse cultural patterns of India through Education and Outreach activities and Operation salvage. |  |  | A: Infrastructure Development Upgrade the visitor facilities in the 200 acre museum campus: expansion of road network, sewerage systems, electrical installations, additional drinking water facility and toilets, children’s park etc. Up-gradation of indoor galleries: Indoor museum galleries would be upgraded with additional exhibits and by providing interactive kiosks. Four more galleries will also be developed with thematic presentations of diversified aspects of Indian culture. Open air exhibitions: to be strengthened with traditional house types from Gujarat, West Bengal, Rajasthan, Haryana, Nilgiri Hills, Western Ghats, Islands and also from N.E. States. Regional Centre, Mysore to be strengthened with equipments and paraphernalia. Strengthening of archival materials to be made to collect nearly 1000 ethnographic specimens from various communities of India. B. Education and outreach programmes to be strengthened by organizing. a. A variety of Do and Learn museum education programme with direct involvement of tribal/ folk artists to promote the vanishing aspects of traditional knowledge and technologies. b. 10 Periodical exhibitions in various parts of India. c. 5 Artists camps and workshop. d. 10 seminar/ symposia/ museum popular lectures. e. 5 Performing Art Presentations of classical, folk and tribal performing art forms in India. f. Documentation of intangible Cultural Heritage of India g. Publications of series on intangible Cultural Heritage of India and other occasional publications/ journal. h. Inter-disciplinary training course on Ethno-Museum Education. Operation Salvage. Take up collaborative anthropological projects in Himachal Pradesh, Madhya Pradesh, Orissa, Karnataka and North Eastern Staes to ensure recapitulation and recirculation of vanishing or languishing knowledge systems. | Construction of introductory gallery for River Valley Culture is under progress and 70% work is completed. Construction of engineering store is completed other than the regular maintenance works. Construction of ramp at library is completed. Regular maintenance work of ethno-botanical trail was carried out. Process for erection of a traditional stone made house from Rasta was completed. A new open-air exhibition entitled Traditional Technology was inaugurated. During the period nearly 928 specimens, 2541 slides/photo prints, 562 vols. Of Indian/Foreign journals and 1026 books were added to museums collection. An open air exhibition is currently being developed by inviting traditional artist from various states. The center also organized 2 seminar, 1 workshop, 4 museum education programmes, 2 performing art presentation etc. An in-service training workshops specially for the curators from Southern Indian States was organized, 7 temporary exhibitions were mounted. 4 ‘Do and Learn’ museum education programmes were organized. 8 seminars, 2 museum popular lectures, 1 annual IGRMS lecture, 9 performing art presentation and special programmes like International Museum Day,Edakkal Festival 2007, National Balrang 2007, World Disabled Day, Tribal Healers workshop etc. were organized. Books, 3 Newsletters, 2nd volume of Journal ‘Human Kind; and other occasional publication were published. Field work for Operation Salvage is a regular feature and is being carried out. |  |  |  |
| 27 | Other Programmes (Museums) |  | 5.69 | 22.64 |  |  | 5.40 | 16.57 |  |
| (a) | National Research Laboratory for Conservation of Cultural Property, Lucknow | To develop the capabilities of different cultural institutions in the country in the conservation of cultural property and provide conservation services to Museum, Archives, etc. | 1.85 | 1.20 |  |  | 1.74 | 1.17 |  |
| (i) | Research in Conservation | To develop and standardize better methods of conservation |  |  | 6 projects including 2 continuing projects from the previous year will be undertaken. | 10 projects including 3continuing projects from the previous year were continued. |  |  | Long term research projects continuing |
| (ii) | Conservation service | To provide conservation services to different museums, art galleries and related departments |  |  | Conservation of maps and drawings of world heritage site CST, Mumbai. Conservation of stone sculptures and Government Museum, Mathura. Conservation of Manuscripts from Rashtriya Sanskrit Sansthan, Allahabad. Conservation of Books, Paintings etc. received from different department in the Southern Region at RCL, Mysore. Objects from other institutions will be attended to for advice and conservation as and when required. | 4 Thankas from State Museum, Lucknow (II) 42 maps from World Heritage Side, CST, Mumbai (III) 5 Manuscripts from Rastriya Sanskrit Sansthan, Allahabad. (IV) Crafts Museum, Lucknow Ivory objects-34 Textiles- 39 Wooden objects-38 Metal objects-30 (V) 3 oil paintings from Raj Bhawan, Lucknow (VI) 3 coins from Aligrah Muslim University (VII) on the recommendation of Ministry establishment of conservation laboratory in High Court Campus, Lucknow (VIII) report on conservation status of artifacts of Dr. Rajendra Prasad Smriti Sangrahalaya, Patna. |  |  | # Completed |
| (iii) | Training in conservation | To impart training to conservators, curators and other museum professionals. |  |  | Six months course on conservation of cultural property. Two weeks orientation workshop on care and maintenance of museum objects. Workshop on preventive conservation of ethnographic museums in the north east. | 1.Workshop on care and maintenance of library material organized. 2.Inter disciplinary workshop on structural conservation organized. 3.Orientation workshop on care and maintenance of cultural heritage organized. |  |  |  |
| (iv) | Regional Conservation Laboratory, Mysore. | To render conservation services in the southern region. Upgradation and setting up of advanced conservation facilities. To undertake research programmes. |  |  | Conservation of Books, Painting etc. received from different department in the southern region. Objects from other institutions to be attended as and when requests are received. Establishment of facilities for conservation. Conservation research programmes in collaboration with National Manuscript Mission. | Documentation, recording diagnostic research & testing of conservation treatment for conservation work on 3 rare books containing 1267 pages in highly damaged condition and a painting in Mysore style completed. About 2000 books were examined. Fumigation of 525 books done. Documentation of 80 books for conservation treatment completed. 4 months training imparted to 3 project assistants. |  |  | In progress different type of art objects have been preserved |
| (b) | Victoria Memorial Hall, Kolkata | Museum of contemporary art involved in collecting material and data relevant to a period depicting art history during the freedom struggle. | 2.30 | 7.00 |  |  | 2.30 | 4.90 |  |
| (i) | Preservation, Restoration and Conservation of Art Objects | To preserve the Cultural Heritage of Modern Indian History (Oil painting, Water Colour Aquatints, Miniature, Lithographs, Manuscripts, Coins, Medal, Arms & Armour etc.) |  |  | - Preventive Conservation of artifacts and frames – 480 oil paintings - Curative restoration/ conservation of 20 paintings - Conservation of 15 nos. antique frames - Conservation of Textile objects – 60 nos.. - Conservation, repair & binding of 30 old rare books of library/Archive. - Conservation of 10 metal objects. - Technical assistance to other organizations like Raj Bhavan and Bhaskar Bhavan. | Curative conservation of 6 oil paintings completed 5 oil paintings are under restoration A team already sent to Agartala for restorations of painting of NE 5 frames completed and 1 under restoration conservation of 13 objects, conservation 250 sheets of Hyde’s Report vol- 14, preventive conservation of 4 textile objects in display at Kolkata gallery. 3 Books and 2 visitor's books were conserved and 8 books are being fumigated. 8 coins and 27 arms & Armours conserved . 4 artifacts water colour from Bhaskar Bhawan being conserved. In addition to this 83 photographs from Raj Bhawan conserved, repaired and refixed. |  |  |  |
| (ii) | Domestic Exhibition | To familiarize the public at large about the richness of the collections and to communicate our past history, culture and aesthetics and atleast one traveling exhibition in any one of the Metropolitan cities in India. |  |  | Four exhibitions on topics related to the collection of Victoria Memorial in bringing out catalogue of the exhibition. One traveling exhibition. | VMH mounted an exhibition at Ganga Festivals Kolkata, photographic exhibition on Raj Bhawan mounted and is going on. |  |  |  |
| (iii) | Publication | To bring out high quality publication and some authentic catalogue on our unique collections of works of European artists and to create awareness of about our culture, history, heritage and aesthetics. |  |  | - Masterpieces of Victoria Memorial. - Catalogue of Arms & Armour and oil paintings - Catalogue on Persian Manuscripts - Reprinting of VM publications and photos. | Publication entitled "Convergences of Sufism and Bhakti" Barackpuer Itihas Monograph based on Himalayan Landscape paintings. Dalhousie Quared and reprinting of postcards, photo albums etc. are in the press. |  |  |  |
| (iv) | Setting up/ Modernization of galleries and storage of art objects including additional lighting installation and air conditioning. | To restructures, remodel all the galleries of the Memorial with proper display, lighting system and air conditioning. |  |  | Modernization of stores 72 and 74, North Porch rooms and Study collections for oil, paper and metals and the Archive and plan for three galleries. | For modernization of stores 72 and 74 and also modernization of galleries, the finalization of agreement on the total estimates of Rs. 71 crores submitted by the NID is under process. |  |  |  |
| (v) | Acquisition (Art Purchase and procurement of art objects and artifacts) | To augment our existing collection of artwork through Art Purchase |  |  | Acquisition of Art objects (Kalighat Paintings, paintings of the artists of Bengal School – Abanindranath, Nandalal Bose, Jamini Roy and their student’s art work of other modern Indian masters. Other historical objects, objects of artistic and historical value relevant to the areas of concern of V.M. | Art purchased committee will meet soon for acquisition of art objects. |  |  |  |
| (c) | Allahabad Museum, Allahabad | The main activities of the museum include acquisition of art objects, reorganization of galleries and reserves enriching the library and photography unit and publication | 1.20 | 1.44 |  |  | 1.12 | 1.12 |  |
| (i) | Renovation of building | Road carpeting and landscaping of campus area of the Museum. Renovation of the gate complex, replacing the old time barrack in a dilapidated condition by waiting Hall, a pantry and a two room guest house. |  |  | It will strengthen the security of the Museum. Additional space will be created for storage and the courtyard after modernization will give a better look | The civil works for repairing of store room, providing aluminum partition in the library hall, renovation of approach to generator room etc. are being taken up. |  |  | Progress dependent on timely availability of funds |
| (ii) | Library | To fill up gaps in the number of journals and volumes of sets acquired by the museum, to microfilm certain books and journals which are not available by sending a team consisting of Museum personnel and to acquire books and journals of importance to enrich the Museum library. |  |  | It will meet the increasing demand of scholars for availability of latest books on various subjects for their study and research work and also enrich the library | 1452 books acquired, 26 issues of journals and 6 newspapers were received in the Museum. 6121 readers attended the library and consulted 401 books by the scholars, 11277 zerox copies were taken out. |  |  |  |
| (iii) | Modernization of galleries | To mount a panorama of civilizations of Middle Ganga Valley and setting up of a new diorama in the Archaeological Gallery to show the advent of man in the Belan Valley. |  |  | Modernization work will be carried out to provide better knowledge of our ancient culture/ heritage | Rubbing of floor in post –Gupta Sculpture and terracotta gallery completed new captions plates fixed. Polishing and painting works in gallery carried out wherever necessary. |  |  |  |
| (iv) | Acquisition of Art Objects | To acquire art objects for the Museum through Art Purchase Committee in its meeting to be held at suitable intervals during the year 2007-08. |  |  | To augment Museum’s collection of antiquities with rare objects. | The art purchased committee of museum met on 17-18 Oct.07 and 2 March 08, after examined various objects of art and antiquities recommended acquisition of art objects. |  |  | It will be ensured that no fake antiquities will be acquired. |
| (d) | National Museum Institute of History of Art, Conservation & Museology, New Delhi | To provide education and training in the specialized areas of art, history, conservation and restoration of artifacts and their display and upkeep in museum. | 0.17 | 3.50 |  |  | 0.11 | 2.38 |  |
| (i) | Academic Programme | Dissemination and advancement of knowledge in the fields of History of Art, Museology and Conservation. |  |  | Conducting of courses by admitting students to M.A. courses (55 seats) and Ph.D. courses (12 seats) as well as running three short terms courses – two in English and one in Hindi (about 250 participants in all). | The enrolment of students under M.A. & Ph.D, and short term courses was 30 and 291 students respectively. 244 books were acquired including 108 gifted books |  |  |  |
| (e) | Scheme for financial assistance for ‘Promotion & Strengthening of Regional & Local Museums’ | To promote the strengthening and modernization of existing museums at the regional, state and local level. | -- | 9.00 | Out of about 150 proposals received from the different museums every year, 50 to 60 museums receive grant every year. | 55 museums/ organizations were given grants amounting to Rs.6.99 cr. during the year under review. | -- | 6.99 |  |
| (f) | Scheme for Modernization of Museums in Metro Cities | In order to bring some of the Museums in the Country at par with the best in the World. | -- | 0.50 | A token provision of Rs. 50.00 lakh has been made. | The scheme has already been given ‘in principle’ approval by PC and will be taken up for implementation in 2008-09. | -- | -- |  |
|  | Total (Archaeology, Archives, Museums) |  | 255.97 | 195.64 |  |  | 250.03 | 191.52 |  |
|  | Public Libraries |  |  |  |  |  |  |  |  |
| 28 | National Library, Kolkata | To serve as a repository of all reading and information materials produced in India as well as abroad concerning India | 15.40 | 7.00 |  |  | 14.14 | 4.71 |  |
| (i) | Collection Building & Book Production Statistics | To collect books and other printed materials published in India, Acquisition of Foreign Books and Periodicals |  |  | National Library targets to acquisition 35,000 Indian publications,3,500 foreign books and 680 titles of Foreign journals . | 20,500 Indian publication and 1,820 foreign books were acquired/ purchased. 480 titles of foreign journal have also been purchased |  |  | The deposits under the Delivery of Books and Newspapers Act, 1954 depend mainly upon cooperation by publishers |
| (ii) | Readers Services | Retro-Conservation, Digitization and Modernization of Laboratory, Preservation Computer Units |  |  | It also intends to digitize 15 lakh pages of old and rare books and retrospective convertion 4 lakh bibliographical records in digital format. | These projects are in the progress with an aim to upgrade the preservation, conservation and computer units of the library for readers. |  |  |  |
| (iii) | Strengthening of Administration | CCTV Installation, Furniture & interior decoration of Bhasha Bhavan etc. |  |  | CCTV on security angle, Furniture for shifting of all divisions to Bhasha Bhavan | The strengthening work and providing facilities in Bhasha Bhawan is under process. |  |  |  |
| 29 | Delhi Public Library | To provide free library and information services to the people of NCT of Delhi and also to provide mobile library services in rural area of Delhi. | 6.90 | 2.50 |  |  | 6.46 | 1.00 |  |
| (i) | Collection Developments | The basic objective of DPL is to provide free library and information services to people of Delhi. In order to achieve this objective, DPL proposes to strengthen its collection development in all the service units. Besides this updating of Reference Collection of Central Library and Sarojini Nagar will also be taken up by acquiring new reading materials. |  |  | Around 4,000 titles (50,000 Multiple Copies to be purchased for the DPL system in English, Hindi, Urdu, Punjabi, Besides audio & video crassest also. | About 55,772 books were purchased upto March 08 books selection process on Hindi, Urdu, Punjabi, Reference book, children books, and DVD are under process. |  |  |  |
| (ii) | Conservation and Preservation | Binding care and repair of books and other reading materials are continuous activity of DPL. Preservation of documents is a compulsion in a library for posterity purpose. |  |  | Around 40-50 thousand volumes are to be bound through commercial book binders. | During the year 15983 books were bound by binders. Books were transferred to binders for binding by the Deptt. |  |  |  |
| (iii) | Modernization and IT Development | Modernization of library activities is the continuous process of DPL. It is proposed to augment the computer system of library, which requires more computer, server, scanner, operating system, ISM etc. for creating of database in other Indian languages. |  |  | It is proposed that the Hindi version of DPL's Website will be made so that more number of reader can access to DPL. It is further proposed to acquire new library software, computers and server and other accessories etc. | Orders for 30 computers with DGS&D have been placed and also accessories for introducing public internet access. |  |  |  |
| 30 | Raja Rammohun Roy Library Foundation | To promote and support public library movements in the country. | 2.10 | 25.00 | Raja Rammohun Roy Library Foundation through their matching schemes intends to assist 9,000 libraries to acquire around 3 crore books, 112 libraries with the provision for mobile units, 2800 libraries with storage materials, 67 organizations for providing awareness, orientation to library professionals,41 libraries for supply of Audio-visual aid and supply of computers for Automation and 85 libraries for construction of library buildings. Under the non-matching schemes, the Foundation intends to give assistance to voluntary organization to set up 340 libraries, assist 157 children libraries or children section of public libraries, 61 libraries to establish children’s corner, procure 1.5 crore books for 469 State Central Libraries and District Libraries etc. 246 libraries to motivate youths. | Under matching schemes, 10684 libraries assisted, 7 organizations assisted for mobile libraries and rural book deposit centre, 2146 libraries assisted towards storage of books, 72 libraries assisted for seminar/ workshop and book exhibitions,158 public libraries assisted for increasing accommodation and 78 libraries assisted for acquiring TV-cum-VCP sets for educational purposed. Under non matching schemes 180 NGOs provided public library services, 281 children libraries assisted, 479 state central libraries and district libraries assisted,. | 2.10 | 24.19 | The timely contributions by the State Governments under the matching schemes is have a bearing on finalization purchases. 37 centrally sponsored libraries assisted, 4 organizations assisted for conducting seminar, conference etc.,23 public libraries assisted for centenary celebrations, 207 DYRCs assisted |
| 31 | Other Libraries |  |  |  |  |  |  |  |  |
| (a) | Central Reference Library, Kolkata | To implement (a) Compilation and publication of the Indian National which is a bibliography of current Indian Publications in Indian languages recognized by the Indian Constitution and in English and (b) Compilation and Publication of Index Indiana. | 1.10 | 0.40 |  |  | 1.06 | 0.20 | Annual volume 2006 MSS ready All monthly issues of 2007 published. System has been rectified, New Server purchased |
| (i) | Indian National Bibliography | a. Publication of Indian National Bibliography Annual Volume 2005 b. Monthly issue of INB 2006 January to December |  |  | 250 copies of Annual Volume of INB 2005 12 monthly issues of 2006 INB | Printing could not be done. MSS return from GOI press, Santragachi. Printing is done through Pvt. press |  |  |  |
| (ii) | Index Indiana 1999-2000 | Compilation and Publication of Index Indiana. |  |  | 100 copies to be printed | Manuscript returned by GOI press. Printing to be done by Pvt. press |  |  |  |
| (b) | Khuda Bakhsh Oriental Public Library, Patna | This Library has been evolved out of a personal collection of Maulvi Mohd. Bakhsh who was a man of letters with a great passion of books. | 1.60 | 2.50 |  |  | 1.34 | 0.21 |  |
| (i) | Acquisition: Purchase of Books, manuscripts, microfilms, Video & Audio Cassettes | To acquire books, manuscripts, microfilms, Audio & Video CDs for use of readers |  |  | Purchase of 5,000 printed books, 50 manuscripts and 120titles of journals | 6 manuscripts, 2 antiques, 67 periodicals,6138 books, 78 periodicals, 128 newspapers, 97 audio, 39 video cassettes and 100 coins were purchased. |  |  |  |
| (ii) | Research & Publication: Publication of rare material , Printing of Catalogue, Research seminars, Lectures & Cultural programmes, Khuda Bakhsh Research Fellowships and Publication of Quarterly Journal. | To bring out critical editions of manuscripts, publish books of rare value, lectures by distinguished scholars. To acquaint the outsiders with the hidden treasure descriptive catalogue. Organization of seminars, lectures of distinguished personalities. Fellowship and Scholarships to renowned scholars. |  |  | Publication of 20 books. Printing of 2 volumes of descriptive catalogue. National Seminar – 1 Annual Lecture – 1 Extension Lecture – 4 Popular Lecture – 12 Senior Fellowship – 3 Junior Fellowship – 7 Publication of 4 issues of Quarterly Journals. | 16 books published 1 vol. Of new descriptive catalogue of MSS published , 4 seminars, 1 annual lecture, 6 extension lectures, 6 popular lectures, 1 workshop ,1 exhibitions, 3 mushaira, and 4 culture programmes organized. | Throughout the year. |  |  |
| (iii) | Conservation & Preservation : Preservation Laboratory and development of books preservation & reprographic facilities | Preservation Lab. For routine maintenance, curative as well as preventive and preservation. To keep the books in the good condition. |  |  | Routine activities for preventive and curative preservations of books and manuscripts. Getting printed books and manuscripts bound on contract basis. | 125 MSS, 272 books repaired and bound, 26962 folios of MSS & books repaired, de-acidified and laminated. |  |  |  |
| (c) | Thanjavur Maharajas Serfoji’s Saraswati Mahal Library, Thanjavur | A priceless of repository of culture and knowledge, it was conceived as the Royal Palace Library in the 16th century. | -- | 0.50 |  |  | -- | 0.29 |  |
| (i) | Publication of books from the manuscripts in Sanskrit, Tamil, Marathi etc. | To translate, transliterate the manuscripts and to bring out books. |  |  | 50 books | The library brought out a numbers of books on Ancient Treaties, Agamas Medicine, Astrology literature etc. |  |  | Taking of micro film is a must though the library is taking up digitization. |
| (ii) | Conservation Micro Film & Computerization | To apply citronella Oil to Palm leaves and to preserve the Paper manuscripts/ Valuable Old books etc. Microfilm of Manuscripts and rare books for preservation. To printout books from the manuscripts as edited by languages experts. |  |  | To clean and apply 600 leaves Manuscripts per day and to clean and preserve 20 books daily. 600 frames daily. 50 books every year | This work is being regularly attended by the organization and application of citronella oil has been proved to give flexibility to palm leaves which is being executed. |  |  | With well equipped computer cell, books are printed through the library. |
| (d) | Central Tibetan Library | Aim to acquire and conserve Tibetan books and manuscripts and to provide intensified reference service as well as Centre for Tibetan manuscripts, paintings and object of Arts. | 0.55 | -- | The ongoing activities of the Library continued to provide research facilities including documentation and written material for regular courses on Buddhist philosophy and Tibetan tradition. | The activities of this library continued to provide research facilities particularly in the field of Buddhist philosophy and Tibetan art & culture. | 0.55 | -- |  |
| (e) | Rampur Raza Library, Rampur | The main objective of the library to acquire and conserve Indo-Islamic manuscripts, miniatures, books and other objects of arts and science in the library and to serve as a center of reference and research and also act as a center of Arts for International importance. | 1.15 | 2.00 |  |  | 0.96 | 1.80 |  |
| (i) | Publication & Printing | Publication of books of text of Arabic, Persian and Sanskrit manuscripts. |  |  | Proposed to publish 6 to 8 books of text of rare manuscripts. | 11 books published | Through out the year. |  |  |
| (ii) | Preservation and Renovation of two Heritage Buildings. | Two historical palaces of Raza Library viz Hamid Manzil and Rangmahal are monuments of archaeological importance. They involve scientific repairs of archaeological or special nature. |  |  | Repair and restoration of badly damaged or fallen ornamental ceilings of Darbar Hall of Hamid Manzil. | The restoration work of false ceiling of bath rook of OSD’s and office at Hamid Manzil. Repair work of roofs with lip type joint at Hamid Manzil and Rang Mahal as well as repair and painting work of reading room have been completed. | Through out the year. |  |  |
| (iii) | Deployment of CISF | To watch and ward of the library assets. |  |  | Deployment of 26 personnel of CISF for safety and security of Library. | 26 security guards were deployed for safety and security of the library | Through out the year. |  |  |
| (f) | National Mission for Manuscripts | Aims at cataloguing, conserving and collecting the invaluable manuscripts from all over the country and to strengthen manuscript resource centers, manuscript conservation centers and digitization of catalogues and prestigious manuscripts. | -- | 8.50 | Curative, conservation of manuscripts-1082 p |  | -- | 6.37 |  |
| (i) | Mapping, Listing, Cataloguing and awareness campaign | Indian Manuscripts are scattered in known & unknown collections across the country, creations of National data base. |  |  | To cover National Survey in 5 more states, Post survey in 7 more states. | Post Survey in 3 states MRC Grant to 32 MRCs |  |  |  |
| (ii) | Formation of MRCs/MCCs | To monitor, Control of the work of identifying, documenting, protecting and making accessible of the manuscripts |  |  | To increase MRCs to 55 from 46 and MCCs to 40 from 33. | MCC Grants to 25 MCCs and 2 MCPCs |  |  |  |
| (iii) | Conservation and training | To conduct workshops to collaborate with digitization to conserve the identified manuscripts. |  |  | To conduct 9 more workshops | 2 workshops held |  |  |  |
| (g) | Setting up of a National Mission on Libraries, leading to the formation of a Commission | To pointedly address the problems of Public Libraries and to upgrade the infrastructure and technological environment of the Public Libraries within a time frame | -- | 0.50 | Token provision has been made to initiate the spade work. | Planning Commission has accorded its in principle approval for setting up of the Mission. | -- | -- |  |
| (h) | State Central Library, Mumbai Modernization/ computerization/ Digitization /Up gradation of state central library | To acquire books and periodicals under the provision of press and registration of Books Act, 1867 and the delivery of Books Act, 1954 and preserve them for posterity. To digitize rare books and manuscripts | 0.30 | 0.20 | In the first phase 10 lakh pages of old / rare books/ manuscripts shall be digitized. Approx. 4 lakh DBA books are to be computerized. | Work relating to Digitized / Retro-conversion of material is in progress. | 0.15 | 0.00 |  |
| (i) | Conemara Public Library, Chennai | It is one of four recipients of Public Libraries under the provisions of the Delivery of Books and Newspapers (Public Libraries) Act of 1954 to receive all materials published in India free of cost. It serves as a UNESCO information center and receives all the publications of UNESCO. It is also a depository for Asian Development Bank Publications. | 0.30 | 0.60 | - Standard works excluding pamphlets, children books etc – 10815. - Newspapers – 272 - Periodical titles etc. – 3106 - The work of Gazette Notification, bulletins, maps, children’s books etc. will be accessioned, processed and maintained. | A number of standard books acquired,. Seminars and computer training for the staff were held and a good number of pages of various books/ documents scanned and also books bound.. | 0.30 | 0.60 |  |
| 32 | Provision for Project/ schemes of N.E. Region and Sikkim |  |  |  |  | # Expenditure figure for development of cultural activities in NE has already been included under respective organization/ scheme |  |  |  |
| (a) | Project/ Schemes for promotion of Art and Culture | To promote, disseminate and protection of art and culture in NE States | -- | 27.65 | Organizing various programmes in the field of art and culture in various cities of the North Eastern States. | Various programmes on development and promotion of art & culture of NE were organized in NER and other parts of the country. | -- | # |  |
| (b) | Archaeology, Archives and Museums | To promote cultural activities in the fields of Archaeology, Archives and Museums | -- | 23.45 | Development of Museums in North East Region and providing financial support to NGOs in N E R in the field of Archival activities. | Conservation of monuments located in Guwahati Circle of ASI, promotion and development of museums in NER & Archival activities were undertaken. | --. | # |  |
| (c) | Libraries | To promote Library activities in the NER | -- | 4.60 | Development of Library activities in North East Region. | Financial assistance for development of libraries in rural & urban areas and many programmes in the field of libraries was undertaken. |  | # |  |
|  | Total ( provision for NER) |  | -- | 55.70 |  |  |  | # |  |
|  | TOTAL (Revenue) |  | 375.61 | 507.00 |  |  | 394.04 | 456.49 |  |
| 33 | Building projects of attached / subordinate offices |  |  |  |  |  |  |  |  |
| 1 | National Gallery of Modern Art | (i) NGMA’s new Wing, New Delhi | -- | 4.00 | Work is under progress | Funds amounting to Rs. 3.00 crore have been authorized to CPWD for new wing of NGMA, Delhi | Will be completed during the year. |  |  |
|  |  | (ii) Manikavelu Mansion, NGMA, Bangalore |  |  | Capacity creation for the galleries. | The work is under progress and Rs. 0.82 crore have been authorized for carryout this work to CPWD Bangalore |  |  |  |
| 2 | National Archives of India |  | -- | 5.00 |  |  |  |  |  |
|  | (i) | Gas based automatic fire alarm and extinguisher system. |  |  | Work is under progress | Works on various projects have been progressing, fund to the tune of Rs. 0.91 crore are authorized by the Ministry in favour of CPWD civil and electrical. |  |  |  |
|  | (ii) | Completion of remaining works such as Air Conditioned Plant, Jaipur. |  |  |  |  |  |  |  |
|  | (iii) | Construction of functional building of record center, Bhubaneswar |  |  |  |  |  |  |  |
|  | (iv) | Proposal for acquiring 0.21 hectares of land adjacent to Record Centre, Pondicherry. |  |  |  |  |  |  |  |
|  | (v) | Upgrading diesel generator set and A/C plant for NAI. |  |  |  |  |  |  |  |
| 3 | Anthropological Survey of India |  | -- | 7.00 |  |  |  |  |  |
|  | (i) | Construction of Office building of Eastern Regional Centre at Salt Lake, Kolkata |  |  | Work is under progress | CPWD Kolkata, Mysore, Udaipur, Daharadun and Jagaldalpur have been authorized an amount of Rs. 3.22 crore to undertake various works situated at these sites. |  |  |  |
|  | (ii) | Construction of residential quarters guest house and Museum of International Standard etc. at Udaipur |  |  |  |  |  |  |  |
|  | (iii) | Construction of Guest House Library, Museum and Conference Hall of North East Regional Centre at Shillong. |  |  |  |  |  |  |  |
|  | (iv) | Construction of residential quarters and guest house of North West Regional Centre, Dehra Dun. |  |  |  |  |  |  |  |
|  | (v) | Construction of an International standard guest house NA ancient lab. At the SRC, Mysore. |  |  | Work is under progress |  |  |  |  |
|  | (vi) | Acquisition of land for Construction for Office Building of the SRC, Jagdalpur and Ranchi Fiedid station |  |  | Work is under progress |  |  |  |  |
| 4 | National Research Laboratory for Conservation of Cultural Property, Lucknow | i. Training Institute in conservation at Lucknow. ii. Dating & Authentication at Regional Conservation Laboratory, Mysore | --- | 6.00 | For important activities of Laboratory, Training Instt.-cum-Hostel/Guest House at NRLCCP, Lucknow. | An amount of Rs. 0.19 crore has been authorized to CPWD Lucknow for carrying out of construction work of hotel-cum-guest house. |  |  |  |
| 5 | National Museum |  |  |  |  |  |  |  |  |
|  |  | Shifting of Air condition plant etc from National Museum campus etc. | --- | 6.00 | Work still to be taken up. | Rs. 0.49 crore authorized to CPWD New Delhi for carrying out civil works. |  |  |  |
| 6 | National Library |  |  |  |  |  |  |  |  |
|  |  | i. Construction of readers’ hostel | --- | 1.00 | Work still to be taken up. | This will be taken up in the next financial year. |  |  |  |
|  |  | ii. Construction of Type-II & III Quarters. |  |  |  |  |  |  |  |
|  | Central Secretariat Library | iii Construction work in Tulsi Sadan Library branch of Central Secretariat Library |  |  |  | Rs. 0.34 authorized by the Ministry in favour of CPWD cir-I |  |  |  |
| 7 | Archaeological Survey of India | Construction of building and staff quarters for ASI at Dharwad, office building at Nagpur, Mysore, construction of Institute of Archaeology at Greater NOIDA, linear building at 24, Tilak Marg, New Delhi etc. |  | 21.00 | Work is under progress | Rs. 9.09 crore have been authorized to CPWD/PWD for carrying out various projects of ASI |  |  |  |
|  | Total (Building Projects) |  | --- | 50.00 |  |  | -- | 13.97 |  |
|  | Grand Total (Art & Culture) |  | 375.61 | 557.00 |  |  | 394.04 | 470.46 |  |